## Workforce
NHS Orkney 2023/24 - Plan on a Page
Progress against key actions
Workforce
Workforce is at the heart of NHS Orkney and our local community. Now more than ever we face profound challenges, and we must take steps to retain the great staff we have through strengthened support and development options whilst attracting the best people to join us.
| Action | Lead | RAG | Q1 Area of Focus | Q1 Progress | Risks & Issues | Controls | Q2 Areas of Focus | Year End Achievement / Outcomes
1 | Acknowledge the range of pressures our workforce face personally and professionally and maximise support for them through a range of actions. | Interim Director of HR | Green | 1. First NHS Orkney Staff Stress Survey (tool is made up of a framework of HSE Stress Management Standards around which a set of questions are based.) to be presented to Area Partnership Forum for approval of roll-out during 2023/24 2. To develop an Endowment Fund bid for a strengthened staff health and wellbeing offer, ready to launch in Quarter 2 | Signed off by SGC May2023. Questions defined for use. Roll out plan is underway and will be aligned to the commencement of new Health and Safety colleagues joining in August. Bid is developed with appropiate supporting documentation. Currently with CEO prior to going to the Endowment Committee. | none identified | none identified | Planning phase for roll-out, including considerations around potential risks and issues impacting the outcomes of the tool Implementation and timeline confirmed - questionnaire to be issued
2 | Invest in leadership and staff development. | Interim Director of HR | Amber | 1. Define the purpose, and scope of a Leadership Development Programme in partnership with NHS Shetland. 2. To upskill staff by investing in a range of training, including how to write good papers, QI fundamentals and presenyation skills | QI fundamentals training organised for FSO and wider staff in project management roles (July 2023) 1. work is currently undeway in the collaboration of the delivery -update to APF - August 2. not identified as a need as part of the signed off training plan ior activity linked to the Staff Governance Action Plan under skills - as a new addition and request we will undertake a TNA - Q2 - what has been delivered to support upskilling staff via the Flexible Workforce Development Fund SVQ 2 - Business & Administrationx 1/SVQ 3 - Business & Administration x2/ SVQ 2 - Social Services & Healthcarex 1/ ECDL 1 (Essentials) x 1/CMI Level 6 First Line Management x 1/Project Management x12/Minuting of meetingsx 6 | 2. Non funded or scope of original TNA and funding for org training- may cost additional funding | TNA output | Commencement of a needs analysis across the organisation focusing on communication to drill into why communication is constantly raised as an issue, what are the blockers and what communication skills require development across the majority Agree the purpose, and scope of a Leadership Development Programme in partnership with NHS Shetland, by end of Augsut 2023. Trial the LDP offering from September 2023 for new starts. Leadership Day 27 Sept for teams and senior managers joint NHSO and OIC
3 | Use the Healthcare Staffing Act to enhance and shape our actions in relation to staffing. | DoNMAHP | Amber | Re-establishment of NHSO HCSA Programme Board to drive preparation for implementation 1 Apr 24 Testing for guidance chapters - C6: Adequate Time for clinical leaders | Focus on the following chapters of the act - 12II – Duty to ensure appropriate staffing: training of staff 12IJ – Duty to follow the common staffing method 12IM – Reporting on Staffing Submit Q1 feedback to SG | Limited assurance around governance structure, systems and processes in place with relevant leadershup to demonstrate compliance in advance of enactment | Programme Board established which will report in to Senior Leadership Team and unward to Board to provide necessary assurance | National 3Cs staffing level tool(s) run(s) * Community Nursing – East/West Mainland community nursing teams, GP isles nurses, health visitors, school nurses w/c 5 Jun & w/c 4 Sep 23 for 2-weeks Testing for guidance chapters - C9 : Staff Training and Consultation | 12IA: Duty to ensure appropriate staffing (Ref to 121C, 121E, 121F, 121I, 121J)" 12IB – Duty to ensure appropriate staffing: agency worker 12IC – Duty to have real-time staffing assessment in place 12ID – Duty to have risk escalation process in place 12IE – Duty to have arrangements to address severe and recurrent risks 12IF – Duty to seek clinical advice on staffing 12IH – Duty to ensure adequate time given to leaders 12II – Duty to ensure appropriate staffing: training of staff 12IJ – Duty to follow the common staffing method "12IL – Training an Consultation of Staff – Common Staffing Method (This specifically relates to Types of Healthcare & Employees Section 121K (1))" 12IM – Reporting on Staffing
4 | Support teams to review their roles, responsibilities and engage with others to promote shared learning and collaboration. | Interim Director of HR | Green | 1. A review of Executive portfolios will be completed 2. Objectives set for each Director | 1.Completed and shared with the organsation. 2. Completed and signed off by Remuneration Committee June New Executive Team portfolios launched 3 July 2023 Executive Director personal objectives set for 23/24 | None identified | Agreement by CLT share with SLT and org | Clear objectives to be set for Senior Management Team colleagues and their services which align to Strategic Priorities for the organisation
5 | Use the Workforce Plan to support succession planning. | Interim Director of HR | Amber | 1. Commence succession planning with the Executive Team and agree an approach that will be used Trust-wide 2. Agree the scope and core project members for a establishment review | 1. To be discussed at CLT 2. HR completed staff under contract work. Finance currently reviewing budgeted staff Succession Planning commenced with Executive Team (July 2023) Phase 1 of the Estabishment Review | 2. Risk that more colleagues will hold contracts of employment than allocated funding | 1. Finance should be completed end of July - HR will then review and have an initial conversation with Exec manager. Systems will then be updated to accurately reflect contractual establishment and CLT/SLT aware of actual true finances for staffing in post vs historic budgeted in post - 2. Vacancy Control Panel via FSO | Establishment review considering the current funded establishment against the current actual establishment (including temporary staffing models). Continuous support and drive for graduate apprenticeships Understand the potential future gap, potential and development support needed. Build plan - linked to North region conversation
6 | Explore how to strengthen our induction and orientation process. | Interim Director of HR | Green | New induction to be implemented in April 2023 following improvement project led by People and Culture but with representation from across NHSO. | Completed - Induction commenced as agreed and signed off by SGC CEO attending induction to meet all new starters (from July 2023) | None identified | Reports on Induction via SGAP | Formal review of feedback from new start colleagues and line managers to ensure further improvements are captured appropriately in relation to onboarding and induction.
7 | Build on learning from Covid, ensure wellbeing and resilience is central to our decision-making processes. | Interim Director of HR | Amber | 1. Empowering staff to lead change in their local areas and implement their own ideas for improvement. | 1. to discuss at SLT - August around how we create small steps of change - review how many NHS Orkney staff have attended NHSO and NHSS SIFS course and who have improvement skills - 2. completion of imatter questionaire/managers to support action planning q2 exploration conversation around the use of 'Trickle'- employee experience platform Improvement project underway in Physiotherapy Services with a focus on leadership, culture, data and service improvement Strengthened health and wellbeing programme in place, including a new Employee Assistance Helpline, and a new reward and recognition programme | Capturing the data and data quality and defining KPIs on how staff feel | imatter board report and executive engagement with teams | Board and CEO led imatter action planning activity - sharing actions and priorities campaign of communication and calander for staff breifings to SLT re directorate performance Board paper August Progress on aspects approved by Endowments Empowering staff to lead change in their local areas and implement their own ideas for improvement

## Culture
NHS Orkney 2023/24 - Plan on a Page
Progress against key actions
Culture
Improving our Culture is at the heart of how we continue to develop as an organisation. It will help us to secure the future that places the needs of those we care for central to how we act, by listening to our users, empowering staff to act, making decisions in a fair and open way, valuing high quality care and building a sustainable future
| Action | Lead | RAG | Q1 Area of Focus | Q1 Progress | Risks & Issues | Controls | Q2 Areas of Focus | Year End Achievement / Outcomes
1 | Using the key engagement forums such as Area Partnership Forum, agree how we will enhance communication internally (across) and outside our organisation. | Chief Executive | Green | Improving staff communications and staff engagement A more focused agenda at APF which focused on the workforce and culture Plan on a Page priorities 2023/24 refreshed Staff Governance Action Plan with priority areas of focus Improved communications and relationships with our local community and partners CEO 100 Day Plan - a lever for change and improvement | 1. All staff monthly briefings commenced May 2023 - attended by CEO and Executive Directors 2. Fortnightly CEO blogs to all staff 3. Further to engagement with APF and wider staff, 5 organisational priorities launched in response to staff feedback for 23/24 with a strong focus on staff health and wellbeing, value, reward and recognition and involving staff in decision-making 4.Informal relationship meetings with key partners and stakeholders (including Exec-to-Exec with OIC, Leader of Council, Chair and CEO meetings and quarterly Members and NHSO Board briefing session, improved external communications, including more proactive comms on issues such as HDU and Macmillan 5. CEO 100-day plan on track for August publication 6. 2023/24 Staff Governance Action Plan, with priority areas, agreed | Ensure consistency and year-round activity | APF work plan under review Executive Team and CEO commitment to improving communications and engagement internally and externally (in personal objectives) | Launch 100-day CEO plan - setting out how we are responding to feedback (August 2023) Alignment of internal communications to strategic priorities (from end oif August) Agreeing APF workplan aligned to Plan on a Page Continued rhythm of monthly internal and external communications | 1. Enhanced communications in place internally and externally re: openness and transparency – including CEO blog, CEO and Executive team briefings and Executive Director comms. 2. Feeding back via internal comms how we are listening and acting on a more regular basis. 3. A 12-month plan for listening to and responding to feedback from staff, so that more real-time feedback is capured and acted on. 4. Improvements to iMatter score for staff feeling involved in decisions from 45% to >50% 5. Overall experience of working at NHS Orkney to improve from 6.4 6. Introduce stengthened health and wellbeing programme and reward and recognition programme for staff - with APF and wider tea input 7. To develop a new culture programme, which enables us to create a culture where staff feel valued, supported, listened to and safe to speak up.
2 | Ensure our Clinical Strategy informs our strategic decision-making process. | Medical Director | Green | N/A | Paper presented to Board in June summarising way forward in terms of reporting against the action | Financial envelope available to support delivery of Clinical Strategy aspirations | Measuring progress on a bi-annual basis against clinical strategy action plan will help to inform level of tolerable risk across services | 6 monthly report to be produced for SLT and Board oversight
3 | Explore development opportunities for staff to support enhanced communication skills. | Interim Director of HR | Amber | iMatter questionnaires issued to allow managers to receive feedback from their teams. Appraisal conversaitons and PDPs. | Cascaded via Exec teams re appraisals and PDPs - training added around minuting meeting and chairing skills | No formal org TNA - see activity taking place under workforce re TNA |  | Action planning phase of iMatter will allow teams to create key focussed areas to enhance their team’s performance and communication. | 1. Personal development plans for staff via appaisals. 2. To create a menu of development and training opportunities accessible to staff. 3. Improvements in Imater score for staff feeling appropriately trained and developed (from 54% > 60%)
4 | Work to ensure governance work is visible and meaningful to staff. | Chief Executive | Green | Clear communications to staff about how decisions are made at NHS Orkney and timely communications about key decisions | New Senior Leadership Team launched 3 July 2023 with new terms of reference and this was clearly communicated across the organisation. A communication is issued after every SLT to staff to update on key discussions and decisions. August 2023 - review of wider operational governance commences so we can ensure this is clear, we minimise duplication and we maximise staff input into decision-making in the organisation. A Committee Chair Communication Working Group is in place to improve communication from the Board Committees back into the organisation | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | A balance of face-to-face and digital communications to maximise reach to staff | Review of wider operational governance One of 5 top priorities is better involving staff in decision-making We will share with staff the opportunities to get involved and have your say via clinical advisory groups, attending and shadowing opportunities at wider governance forums, including SLT, and a range of listening and drop in opportunities throughout the year as we develop a 12 month rhythm.of how we listen to and respond to staff feedback | 1. New Senior Leadership Team from 1 July, which is clinically-led, and in response to staff feedback re: how decisions are made. 2. Review of operational governance Q 2&3 3. Clear communications to staff about how decisions are made at NHS Orkney and timely communications about key decisions. 4. Improvement in iMatter scores for staff feeling well informed (from 63% > 70%)

## Quality & Safety
NHS Orkney 2023/24 - Plan on a Page
Progress against key actions
Quality & Safety
Quality and Safety is critical to ensure we are delivering the best for those who need our care. Focusing on the experience of our patients and the outcomes they achieve will build confidence that we are delivering the highest quality care for our local community
| Action | Lead | RAG | Q1 Area of Focus | Q1 Progress | Risks & Issues | Controls | Q2 Areas of Focus | Year End Achievement / Outcomes
1 | Use latest guidance to ensure meaningful patient feedback mechanisms are in place which demonstrate that we listen, act, and learn. | Medical Director | Red | Consider use of Care Opinion to capture patient experience/feedback in a more rounded way | Patient Experience Officer and Patient representatives invited to participate in the Pain Serivce review project | Capacity within existing team. Potential that patient feedback is received via areas outwith Patient Experience and not recorded or co-ordinated | Develop mechanisms to capture patient experience across the entire service including systems within the Clinical Admin team | Paper to be presented to NHSO Board in Aug for discussion and plan future activity in this area. | Embedding existing systems within NHSO ways of working
2 | Empower staff to make changes to improve care. | Medical Director / DoNMAHP | Green | Regular listening session and drop-in events for staff | DoNMAHP IP2 and MacMillan listening session, to discuss reintroduce of symptom control as a model of care in MacMillan.Clinical Nurse Managers have completed induction including spending time with colleagues in NHSH, both now have identified portfolios to lead | Some staff will still feel disenfranchised as the breadth of discussions has not taken place as yet due to operational challenges and structure | Interactive monthly all staff briefing with Chief Executive and Coporate Leadership Team | Operational governance review Utilisation of CAIR dashboard to inform decision making and identify areas for implemenation of improvement methodologies Embed of the principles in relation to HSCA | Excellence in Care can be evidenced through performance reporting
3 | Support staff to learn when things don’t go as planned. | Medical Director | Green | Training Plan to be approved, based on an organisation training requests for 2023/24, which includes a request for training from Clinical Governance to train 12 colleagues on significant adverse events. This course will allow colleagues when trained to participate in reviews to support the wider organisation when things don't go as planned | Increased in the number of individuals trained as SAER investigators. This means that staff are supported appropriately through the investigation process | Still insuffiencient numbers of invesitgators further work is required to address this. | Train more individuals | A further 3 staff memebrs are undertaking training in August. | Sufficient personnel trained as investigators to achieve timely investigation of SAER and implementaiton of action plans
4 | Continue to embed the Serious Adverse Events and learning form incidents process. | Medical Director | Amber | Training request submitted by Clinical Governance to train 12 colleagues on significant adverse events. This course will allow colleagues when trained to participate in reviews to support the wider organisation when things don't go as planned | A system has been developed to embed tracking of identifiied SAER learning as part of the Quality Forum Terms of Reference | If NHSO fails to learn lessons from SAERs that mistakes will be repeated and patients put at risk | By reviewing the action log on monthly basis necessary actions can be monitored and themes identified | Bring SAER action tracking into business as usual for Quality Forum | Bring SAER action tracking into business as usual for Quality Forum
5 | Explore where single points of failure exist what can practically be done to address these. | Medical Director | Amber | Explore where single points of failure exist what can practically be done to address these. | Review of clinical pathways and SLAs has commenced. Information being gathered via weekly waiting times meeting. | Capacity within wider team to undertake work beyond the core responsibilities | Seek support from FSO | A review of all clinical pathways, supporting SLAs, and associated data requirements will start in Q1 and be complete by Q4. This will help to identify single points of failure and areas of service fragility which can then be addressed. | To fully understand the fragile services impacting on Orkney and what mitigations can be undertaken
6 | Ensure learning from the HSE visit is acted on and risk management is firmly embedded with visible leadership present in all teams. | Medical Director / Interim Director of HR | Amber | Refreshed Risk Management Strategy and Risk Management Forum Terms of Reference to be produced and approval through RMF and Audit and Risk Committee. Oversight of Risk Management to be reported to SMT, Audit and Risk and the Board. Risk Owners and Handlers to meet with the Clinical Governance and Risk Facilitator on a pre-agreed timeline to ensure risks are captured and updated at all times | The Interim Director of Human Resources has completed the relevant activities linked to the HSE and this has been signed off at the Board in 2022. Activities aligned to the HSE outwith training sit under the relevant Exec Directors, Mental Health DH&SC/Risk - MD/Patient Notes - DNMAHP&Acute | Process for raising and monitoring risks is robust but heavily relies on facilitation by the Health Care Governance Team | Risk Owners/Handlers to be accountable and responsible for updating risks within Datix | Risk Management Strategy to be approved by Board and appropriate policy updates progressed following approval. Oversight of Risk Management to be reported to SMT, Audit and Risk and the Board. Risk Owners and Handlers to meet with the Clinical Governance and Risk Facilitator on a pre-agreed timeline to ensure risks are captured and updated at all times | The Risk Management Strategy and wider processes are well understood and adhered throughout NHSO

## Systems & Governance
NHS Orkney 2023/24 - Plan on a Page
Progress against key actions
Systems and Governance
Systems and Governance supports everyone working in the organisation to know the way we work is aligned to our values, is fair and that decisions made will be consistent.
| Action | Lead | RAG | Q1 Area of Focus | Q1 Progress | Risks & Issues | Controls | Q2 Areas of Focus | Year End Achievement / Outcomes
1 | Continue our focus on strengthening governance processes across NHS Orkney services. | Chief Executive | Amber | Consider approach for Senior Leadership Team | 3 July 2023 - new SLT launched Review of Committee Communications being led by Chair | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | A balance of face-to-face and digital communications to maximise reach to staff | Following a relaunch of Senior Leadership Team, which will become a formal part of NHS Orkney’s operational governance arrangements. Ensuring governance re: IJB and delegated services is equally robust and well understood within NHS Orkney and across wider system RCPE Board Development work to improve assurance and governance | 1. Following a relaunch of Senior Leadership Team, which will become a formal part of NHS Orkney’s operational governance arrangements 2. Extended Senior Leadership Team Meetings to commence Quarter 3 – and to strengthen engagement with wider leadership community across NHS Orkney 3. A review of operational governance Quarters 2 & 3
2 | Empower staff to make decisions in a collaborative, open and transparent way. | Chief Executive | Amber | Regular listening session and drop-in events for staff. | Monthly listening and drop in events for all staff | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture | One of 5 big areas of organisational focus is better involving staff in decision making - clinical and non-clinical opportunities which will be clearly shared with staff, including attendance and input at clinical advisory committees, ADP, Staff Health and Wellbeing Group and wider forums Operational Governance Review | 1. Regular listening session and drop-in events for staff 2. Operational governance review
3 | Learning from Covid remains a priority, ensuring we are mindful of the wider impact on health and wellbeing across our community. | Chief Executive | Amber | Upskilling FSO/Improvement team, exploring test for change cases | Physiotherapy Service improvement plan underway - with focus on leadership, culture, data and service improvement QI fundamentals training for FSO, Project Managers, Clinical Governance, Public Health, Clinical Nurse Managers and Senior Charge Nurses | Creating a learning culture at NHS Orkney and across the system is in its infancy | Working towards developing an improvement function at NHS Orkney and in the meantime maximising opportunities to listen and learn and share learning, including from complaints and incidents | Continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge. Empowering staff to lead change in their local areas and implement their own ideas for improvement Scoping a new Improvement Function | 1. Continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge 2. Empowering staff to lead change in their local areas and implement their own ideas for improvement 3. Having a new Improvment Function in place
4 | Services must not make patients suffer because we do not wish to change, we need to share information, collaborate, and ensure an effective flow across organisational boundaries. | Chief Executive | Amber | Having a plan to respond to the updated Planning with People Guidance Having clarity on our plans to further digitise and improve information flows | Physiotherapy Service improvement plan underway - with focus on leadership, culture, data and service improvement QI fundamentals training for FSO, Project Managers, Clinical Governance, Public Health, Clinical Nurse Managers and Senior Charge Nurses Paper to Board (June 2023) with NHSO's response to the Planning with People Guidance | Capacity to dedicate time to strategic work is limited | Clear pieces of work are agreed with timescales to ensure this moves forward, linked to portfolio changes agreed in Quarter 1 | Data sharing agreement to be in place between NHS Orkney and Orkney Islands Council. A further focus on reducing health inequalities, consistent with the focus in our Clinical Strategy. Update to October Board re: Planning with People Guidance response | 1. Data sharing agreement to be in place between NHS Orkney and Orkney Islands Council 2. A further focus on reducing health inequalities, consistent with the focus in our Clinical Strategy
5 | Build on the communication successes to grow our impact. | Chief Executive | Green | New quarterly informal briefing session with members at Orkney Islands Council and NHS Orkney Board. Strengthened relationships with local media briefings and meetings via Chair and CEO. Strengthened internal communication from CEO and Executive Team. CEO 100 Day Plan | Additional informal sessions with OIC have commenced - Exec to Exec and Board and Members CEO 100 Day Plan published - which focuses reconnecting with staff and the local community Quarterly media briefings with Chair and CEO have commenced Monthly all staff briefings in place and regular CEO and Executive Team comms in place | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about. Limited capacity in Communications. | To ensure equal focus between face-to-face and digital communications Review capacity required in the Communications Team | Informal briefing session with members at Orkney Islands Council and NHS Orkney Board. Strengthened relationships with local media briefings and meetings via Chair and CEO and regular Chair and CEO meetings with politicians | 1. New quarterly inform briefing session with members at Orkney Islands Council and NHS Orkney Board 2. Strengthened relationships with local media, via quarterly briefings and meetings via Chair and CEO 3. Strengthened internal communication from CEO and Executive Team
6 | Strengthen training for leaders and managers to allow decision-making to take place at an appropriate level. | Interim Director of HR | Amber | Revamped SLT/agreed Terms of Reference/Commencement of meetings | To commence conversations around elements of management skills eg finance and budgetary management for non finance managers | Capacity constraint of small teams | TNA | Improve support for managers at induction stage. Create clear operating procedures to explain what is required from managers when it comes to 1-2-1s, valuing staff, supporting staff development, keeping staff well-informed and holding annual appraisals | 1) Better support managers at induction stage, including being clear about what we expect from managers at NHS Orkney when it comes to 1-2-1s with line reports, valuing staff, supporting staff development, keeping staff well-informed and holding annual appraisals

## Sustainability
NHS Orkney 2023/24 - Plan on a Page
Progress against key actions
Sustainability
Sustainability has to be a goal that we strive for, not only environmentally but also financially and from a workforce perspective. NHS Orkney has profound challenges that will require consistent and multi-year efforts to achieve sustainability.
| Action | Lead | RAG | Q1 Area of Focus | Q1 Progress | Risks & Issues | Controls | Q2 Areas of Focus | Year End Achievement / Outcomes
1 | Support the organisation to achieve a sustainable future by using the Clinical Strategy, Workforce plan and Financial Sustainability Plans to inform and shape our decisions. | Director of Finance | Green | Create a Planning Hub to support a collaborative approach. Production of Annual Delivery Plan and Medium-Term Plan | Draft documentation has been started to describe the benefits of a Planning Hub approach (Terms of Reference, Key Stakeholders and Planning Cycle) to be shared with SLT for approval Annual Delivery Plan submitted to SG awaiting formal feedback letter. Engagement sessions completed for Medium-Term Plan and draft being produced | Risk around capacity for colleagues and services with competing demands between proactive planning and 'getting the job done'. Challenges around submission deadlines both locally and nationally to allow optimum alignment and coherence around Strategic Planning. | Clear remit for Planning Hub to support better coherence and utilisation of plans which currently exist. Outcomes of the Planning Hub to be reported through SLT. Annual Planning Cycle to be produced and approved through SLT and Board, which ensures appropriate oversight via Governance Meetings and Committees. | Finalise documentation for Planning Hub and present to SLT for approval. Undertake lessons learned from Planning approach for 2023/24 | Planning Hub established. Strategic Planning for the organisation incorprates a high level overview of Service Delivery, Financial, Workforce and Digital Plans.
2 | Use Net Zero as a driver for change in our models of care. | Director of Finance | Green | National Green Theatres project being scoped to understand opportunities which can be progressed locally. Updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. Model Meeting paper template includes consideration around sustainability to ensure oversight by Governance Committees | Meeting has taken place with National Lead for Green Theatres programme and update shared with Sustainability Steering Group. All meeting papers submitted to Governance Committees/Meetings require reference to sustainability impact. | Capacity challenges potentially limit the opportunities for colleagues/services to embrace sustainable change. | Oversight relating to sustainability through Model Meeting paper template. Progress updates to Finance and Performance Committee. | Updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. Ensure that using net zero is included as a driver for change in improvement work through Financial Sustainability Office, with further assurance through Grip and Control reporting | Improved reporting in relation to performance against Net Zero targets. Green Theatre programme embedded. Phase 1 of Decarbonisation project delivered.
3 | Continue the progress of the multi-year financial recovery plan by getting ownership across the organisation. | Director of Finance | Amber | FSO workplan to be approved by SLT | First round of Confirm and Challenge sessions took place. Grip and Control Board established. Executive Leads have agreed key schemes which FSO will support | Capacity challenges potentially limit the opportunities for colleagues/services to embrace sustainable change. Cost pressures experienced by the organisation can impact on the benefits realised via improvement work. | Financial recovery plan updates shared with key stakeholders through SLT, Finance and Performance Committee and Board. Progress is monitored through Grip and Control Board and Confirma and Challenge sessions. | Upper and lower levels of confidence for each scheme to be identified. Confirm which schemes should be prioritised based on the improvement capacity available to support. | Delivery of £3.7m savings (£1.5m recurring and £2.2m non-recurrng) Delivery of savings schemes across Executive Workstreams.