## ALL >2
Appendices
APPENDIX 1 Audit Recommendation report status
Audit Recommendations
Number | Report | Recommendation | Action Owner | Grade | Original date | Current Timescale | Revised Timescale | Status | Management Response | Update April 2023 | Update May 2023 | Update August 2023 | RAG - percentage complete | Internal Audit agreement to close/comments
236 | Joint Working Arrangements 2022/23 | Nhs Orkney should feedback to the IJB that both the Strategic Plan and Delivey Plan developed for the Orkney Health and Social Care Partnerhsip should be approved and implemented at the start of each financial year. By ensuring these plans are in place and appropriately communicated to all relevant stakeholders, it will allow for clearer direction of the delivery of shared strategic objectives from the key partners in the partnership. The Delivery Plan 2022-25 should also include the roles and responsibilities of those responsible for achieving those shared objectives. | Director of Nursing and Acute Services | 3 |  | June 2023 | 2023-10-01 | On-going | Will action the plan as set out to ensure communication channels and engagement from key stakeholders is affected |  | DoNMAHP / Acute to review this action and timeline with Chief Officer IJB. Communication yet to be drafted as key senior roles have recently become vacant with interims now appointed. | Recent interviews to vacant posts - posts not filled, next steps discussion with Chief Officer IJB to facilitate conversations. |  | Agree revised timescale.
238 | Joint Working Arrangements 2022/23 | It is important for more robust and proactive performance monitoring, such as the intention for plans to monitor and report on strategic performance via the newly updated IJB Performance and Audit Committee. This should be appropriately communicated to key stakeholders within the partnership to ensure all the relevant members of the partnership is aware of plans; how this is then reported back into the governance structure of NHS Orkney should be overtly confirmed. It is also recommended that the strategic and supplemental commissioning strategic plan be approved and implemented at the beginning of the Financial Year. | Director of Nursing and Acute Services | 3 |  | 2023-03-31 | 2023-05-31 | Complete | Agree that this requires action and a plan of delivery will be set out to ensure assurance and monitoring. Agree that strategic and supplemental commissioning will be approved and implemented before 31/3/23 |  | The DoNMAHP now attends the IJB Performance and Audit Committee. Further discussion is required in regard to governance. DoNMAHP will use this mechanism by way of update to the relevant parties. | DoNMAHP also now attending Strategic Planning Group - COMPLETE |  | Agree as closed.
239 | Safeguarding: Adult Support and Protection 2022/23 | To ensure that multi-agency training is delivered to appropriate staff at the relevant time, NHS Orkney should ensure that the position of Multi-Agency Protection Lead is filled as soon as possible. NHS Orkney should ensure that the new Public Protection modules are made mandatory for all relevant staff as soon as possible. Staff should be reminded of the importance of completing this training; finalising the Public Protection Training Strategy to help reinforce this position. Once the mandatory adult support and protection training is rolled out, NHS Orkney should monitor its completion and consider undertaking follow-up activity with staff to understand that the learning has been embedded. | Director of Nursing and Acute Services | 3 |  | 2023-09-30 | 2023-10-01 | On-going | Agree and partially actioned, Multi-Agency training to be embedded and established across the partnership. Level 1 and 2 training has been implimented and agreement reached that this should and is now mandatory across all staff groups, compliance and uptake to be monitored. Modules rolled out are the national modules and not those previously utilised local adaptations |  | Due to longterm sickness of the Public Protection Lead a defined training strategy and strategic plan is yet to be agreed. Turas complaince with roll out of Level 1 and 2 training is to be undertaken at the end of May 2023. | Turas compliance data not been reviewed as yet, priority for Septemeber in the absence of Public Protection Lead. Work underway with NHS Shetland to support and share SOP's and frameworks |  | Agree revised timescale.
242 | Safeguarding: Adult Support and Protection 2022/23 | Whilst in both cases where delays were noted to recording of cases there were other mitigating factors, there is a need to be more explicit in required reporting timescales. For example, whilst it was identified that there was an adult at risk of harm as a branch of the child safeguarding case, processes should be clearer that the issue should also be logged at the first instance of awareness, irrespective of other factors to be considered. We recommend that NHS Orkney reinforces the need to report issues as a matter of urgency, to enable appropriate processing and issues of potential harm to be addressed swiftly. Training should be provided where necessary. | Director of Nursing and Acute Services | 3 |  | 2023-07-31 | 2023-10-01 | On-going | Agree with the recommendation |  | Work has stalled around the IRD process due to longterm sickness within the team. Work has progressed with the roll out and uptake of multi agency use chronologies, with the recent ASP Inspection highlighting this as a positive addition to practice. | Work underway with NHS Shetland to support and share SOP's and frameworks and they continue to support IRD process in Childrens's services especially. |  | Agree revised timescale.
244 | Clinical Governance 2022/23 | NHS Orkney should ensure it assigns relevant responsibilites to address the key person risk that has formed in order to progress both the implementation of the Clinical Strategy and other associated documentation. In particular, NHS Orkney should: - Ensure an action plan is developed to clearly linked ambitions to SMART principles in order to track priorities to completion - Develop and progress associated operational plans to advance the completion of action plans - Consider other areas within the Medical Director's responsibilities and ensure these are appropriately reallocated (or if not fully so, that the risk/ impact is overtly recorded and understood by key stakeholders) | (Interim) Medical Director | 3 |  | 2023-07-31 | 2023-10-01 | On-going | Discussion between (interim) Medical Director and Director of Nursing and Acute Services to divide the areas of responsibility and delegate to the appropriate person to creat SMART objectives for the recommendations |  |  | Clinical Strategy delivery plan will be taken to October Board Meeting |  | Agree revised timescale.
246 | Waiting Times 2022/23 | NHS Orkney should consider implementing additional controls and/ or longer lead times in the forward looking assessment to identify patients that are at risk of being in breach of the required treatment timeline. This may include more structured monitoring as the deadline approaches. | Waiting Times Co-Ordinator | 3 |  | 2023-07-01 |  | Complete | A review of the Standard Operating Procedure in relation to communication to be undertaken to consider opportunities to avoid breaching the timeline wherever possible. |  |  | Trak reviewed for potential breeches. Any breeches are referred to relevant department for follow up and action. Outliers sent to clinical admin for further investigation - COMPLETE |  | Agree as closed.
247 | Waiting Times 2022/23 | NHS Orkney should identify relevant further action to address weaknesses in performance, being as specific as possible with improvement actions/ plan. This will enable NHS Orkney to demonstrate that reasonable action has been talken to optimise waiting times for patients. | Planning, Performance and Risk Manager | 3 |  | 2023-10-01 |  | On-going | A review of reporting in relation to performance is currently underway to ensure that the information in being fully utilised to address obstacles to success and tackle any areas of concern. With clear action plans supported by the reponsible service lead.
248 | Shared Services 2022/23 | The SLAs should be updated to document how both parties will communicate, and how ofter meetings should take place between NHS Orkney and the provider to ensure that performance is discussed and monitored on a regular basis throughout the duration of the contract. KPIs for all shared services should be defined and monitored on a regular basis | Medical Director/ Planning, Performance and Risk Manager | 3 |  | 2023-12-15 |  | On-going | A review of SLAs which is currently underway will include the introduction of appropriate KPIs for all shared services. An agreed communication strategy is currently being undertaken.
249 | Shared Services 2022/23 | NHS Orkney should establish a set of key metrics for SLAs and ensure they have the resources in place to monitor performance on a frequent basis and the data is consistently reported within the performance Management Reports. KPI performance data should be shared with the Board to confirm where improvements in the quality of services and patient outcomes need to be made, to aid effective decision making and guide priorities towards the quality of services provided. | Planning, Performance and Risk Manager | 3 |  | 2023-12-15 |  | On-going | A review of SLAs is being undertaken; data will be used to both understand the demand to ensure the SLAs are fit for purpose, but also to highlight areas for improvement as they progress through the agreed cycle.