## Cover Page
Annual Delivery Plan Template Template: ADP 2 February 2023 NHS Board: Orkney Last updated 05/07/2023 12:47

## Annual Delivery Plan 23-24
Annual Delivery Plan 23-24 | [10 empty] | Quarter 1 Update |  |  |  |  | Quarter 2 Update |  |  |  |  | Quarter 3 Update |  |  |  |  | Quarter 4 Update
Recovery Driver Please select from the drop down list: | SG ADP Action Reference Please select from the drop down list: | NHS Board Deliverable Reference Please create your own reference code for this deliverable | Deliverable Summary Please include a brief summary of the deliverable, briefly outlining the intended action and what this will achieve in 23/24. | Q1 Milestones Please outline what you intend to have achieved by Q1 | Q2 Milestones Please outline what you intend to have achieved by Q2 | Q3 Milestones Please outline what you intend to have achieved by Q3 | Q4 Milestones Please outline what you intend to have achieved by Q4 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list . | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q1 RAG Status | Progress in Q1 Please outline what you have achieved in Q1 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q2 RAG Status | Progress in Q2 Please outline what you have achieved in Q2 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q3 RAG Status | Progress in Q3 Please outline what you have achieved in Q3 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring. | Q4 RAG Status | Progress in Q4 Please outline what you have achieved in Q4 | Risks and Issues - Category Please indicate the types of risk(s) and/or issue(s) impacting on delivery of milestones. Please choose all that are relevent from the list. | Risks and Issues - Description Please provide a short summary of risk(s) and/or issue(s) with a focus on cause and impact i.e. what is the specific area at risk and how will it impact on objectives/milestones. | Controls Please sumarise the key controls in place to manage the risk(s) and/or issue(s), to reduce the impact, or to reduce the likelihood of a risk from occuring.
1. Primary and Community Care | 1.4 | 2023/24QS-0027 | Set out a plan and approach to be taken forward to support early detection and management of key cardiovascular risk factor conditions: diabetes, high blood pressure and high cholesterol | Plan for smoking cessation in development following options appraisal. Begin to plan for additional elements which are protection and preventation. Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded | Discussion with GP Cluster to agree way forward Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded | Following initial discussion with GP cluster ensure a clear and measured action plan is created to address Develop multiagency plan for smoking cessation Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded Report completion of physical activity pilot which will support recomendations in relation to incorpate physical activity in weight management | Review and discuss progress against action plan through GP Cluster Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded Catch up on those missed during COVID who may benefit from the Control It programme | Other | Capacity for key stakeholders to engage and support key actions for the group to ensure success | Reporting through Senior Leadership Team and Assurance to Joint Clinical and Care Governance Committee | Amber | Smoking Cessation support referred option explored through multi-agency group, to begin actioning in Q2. Continued delivery of T2DM framework and HW standards. PA project continuing to be delivered, plan to support health psychology staffing considered and Tier 1 child health group commencing. | Other | Capacity for key stakeholders to engage and support key actions for the group to ensure success | Reporting through Senior Leadership Team and Assurance to Joint Clinical and Care Governance Committee | Amber | Continued deliver of T2DM framework and HW standards. PA project completed to be reported in Q3. Second Nature continuing to be delivered at Tier 2. Early years funding bid submitted to support Henry project. | Other | Capacity for key stakeholders to engage and support key actions for the group to ensure success | Reporting through Senior Leadership Team and Assurance to Joint Clinical and Care Governance Committee
1. Primary and Community Care | 1.6 | 2023/24QS-0028 | Undertake a review of performance data to understand requirements in relation to increasing capacity for provision of in-hours routine and urgent dental care for unregistred and deregistered dental patients | Meeting with SG to provide assurance and improvements are being monitored and obstacles to success addressed. Updates provided to Chief Exectuive and Chief Officer to provide assurance | Meeting with SG to provide assurance and that improvements are being monitored and obstacles to success addressed. Updates provided to Chief Executive and Chief Officer to provider assurance Health Intelligence and Primary Care to work together to create a performance dashboard which helps to identify opportunties for service improvements | Meeting with SG to provide assurance and that improvements are being monitored and obstacles to success addressed. Updates provided to Chief Executive and Chief Officer to provider assurance | Meeting with SG to provide assurance and that improvements are being monitored and obstacles to success addressed. Updates provided to Chief Executive and Chief Officer to provider assurance | Other | Capacity - There is currently a risk that the capacity to report locally does not meet the needs of the organisation | Reporting through Senior Leadership Team and Assurance to Joint Clinical and Care Governance Committee | Green | Met regularly to review data with Practitioner Services to provide assurance and capture that improvements are being monitored and obstacles to success addressed. Updates provided to Chief Executive and Chief Officer to provider assurance | Other | Capacity - There is currently a risk that the capacity to report locally does not meet the needs of the organisation | Reporting through Senior Leadership Team and Assurance to Joint Clinical and Care Governance Committee | Amber | Met regularly to review data with Practitioner Services to provide assurance and capture that improvements are being monitored and obstacles to success addressed. Updates provided to Chief Executive and Chief Officer to provider assurance | Other | Some challenge in terms of reporting capacity | This will be picked up by the Director of Dentistry as part of the 3 month induction
10. Climate | 10.1 | 2023/24SU-0025 | Use Net Zero as a driver for change in our models of care. | National Green Theatres project being scoped to understand opportunities which can be progressed locally Updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. Model Meeting paper template includes consideration around sustainability to ensure oversight by Governance committees | Updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. | A review through the Sustainability Group to understand the actions taken to drive NetZero when considering models of care and obstacles to success Updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. | Updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. | Absence | Absence - Capacity can often mean that the organisation has 1 subject matter expert. In the event that the subject matter expert is absent from work for a prolonged period of time ability to deliver could be impacted | Oversight of progress and obstacles to success will be managed through the Sustainability Steering Group | Green | Meeting has taken place with National Lead for Green Theatres programme and update shared with Sustainability Steering Group. All meeting papers submitted to Governance Committees/Meetings require reference to sustainability impact. | Absence | Absence - Capacity can often mean that the organisation has 1 subject matter expert. In the event that the subject matter expert is absent from work for a prolonged period of time ability to deliver could be impacted | Oversight of progress and obstacles to success will be managed through the Sustainability Steering Group | Green | Updates have been provided by Head of Estates and Facilities to Finance and Performance Committee in relation to Decarbonisation Project (Net Zero). Deputy Head of Estates and Facilities invited to join Planning Hub, to ensure that Sustainability/Net Zero is captured in planning. Meetings continue in relation to Green Theatres project. | Absence | Absence - Capacity can often mean that the organisation has 1 subject matter expert. In the event that the subject matter expert is absent from work for a prolonged period of time ability to deliver could be impacted | Oversight of progress and obstacles to success will be managed through the Sustainability Steering Group
8. Workforce | 8.1 | 2023/24SG-0018 | Continue our focus on strengthening governance processes across NHS Orkney services. | Consider approach for Senior Leadership Team | Following a relaunch of Senior Leadership Team, which will become a formal part of NHS Orkney’s operational governance arrangements A review of operational governance | Extended Senior Leadership Team Meetings to commence Quarter 3 – and to strengthen engagement with wider leadership community across NHS Orkney A review of operational governance | Receive feedback to measure success of change | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | Operational Governance to be reviewed and assurance provided to Board A balance of face-to-face and digital communications to maximise reach to staff | Amber | 3 July 2023 - new SLT launched Review of Committee Communications being led by Chair | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | Operational Governance to be reviewed and assurance provided to Board A balance of face-to-face and digital communications to maximise reach to staff | Amber | New Senior Leadership Team started meeting in Juny 2023 to ensure faster and more clinically-led decision-making RCPE Board Development work progressing with further sessions on Clinical Governance, Board Assurance and projects to take this work forward | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | Operational Governance to be reviewed and assurance provided to Board A balance of face-to-face and digital communications to maximise reach to staff
2. Urgent and Unscheduled Care | 2.1 | 2023/24SG-0020 | Learning from Covid remains a priority, ensuring we are mindful of the wider impact on health and wellbeing across our community. | Plan for Cost of Living Criss for NHS Orkney to be prepared and presented to ACF/APF Share information with OIC to support fuel poverty strategy Contribute to cost of living community partnership delivery group to support the delivery of child poverty strategy and implementation plan Staff development to maintain Health Protection resilence within the team to support reactive Health Protection work | Continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge Empowering staff to lead change in their local areas and implement their own ideas for improvement | Measure and report on success and obstacles to success in relation to continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge Empowering staff to lead change in their local areas and implement their own ideas for improvement | Collaborative approach with OIC to create a fuel poverty strategy Measure and report on success and consider obstacles to success in relation to continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge Empowering staff to lead change in their local areas and implement their own ideas for improvement | Other | Creating a learning culture at NHS Orkney and across the system is in its infancy | Reporting through Senior Leadership Team and Assurance to Staff Governance Committee Working towards developing an improvement function at NHS Orkney and in the meantime maximising opportunities to listen and learn and share learning, including from complaints and incidents | Amber | Physiotherapy Service improvement plan underway - with focus on leadership, culture, data and service improvement QI fundamentals training for FSO, Project Managers, Clinical Governance, Public Health, Clinical Nurse Managers and Senior Charge Nurses | Other | Creating a learning culture at NHS Orkney and across the system is in its infancy | Reporting through Senior Leadership Team and Assurance to Staff Governance Committee Working towards developing an improvement function at NHS Orkney and in the meantime maximising opportunities to listen and learn and share learning, including from complaints and incidents | Amber | QI training session for NHSO staff/leaders Local improvement projevt in place - being led by the Physiotherapy Team | Other | Creating a learning culture at NHS Orkney and across the system is in its infancy | Reporting through Senior Leadership Team and Assurance to Staff Governance Committee Working towards developing an improvement function at NHS Orkney and in the meantime maximising opportunities to listen and learn and share learning, including from complaints and incidents
2. Urgent and Unscheduled Care | 2.1 | 2023/24SG-0021 | Services must not make patients suffer because we do not wish to change. We need to share information, collaborate and ensure an effective flow across organisational boundaries. | None Planned | Data sharing agreement to be in place between NHS Orkney and Orkney Islands Council A further focus on reducing health inequalities, consistent with the focus in our Clinical Strategy | None Planned | Review impact of quarter 2 milestones | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadership Team and Assurence to Information Governance Committee Clear pieces of work are agreed with timescales to ensure this moves forward, linked to portfolio changes agreed in Quarter 1 | Green | Physiotherapy Service improvement plan underway - with focus on leadership, culture, data and service improvement QI fundamentals training for FSO, Project Managers, Clinical Governance, Public Health, Clinical Nurse Managers and Senior Charge Nurses Paper to Board (June 2023) with NHSO's response to the Planning with People Guidance | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadership Team and Assurence to Information Governance Committee Clear pieces of work are agreed with timescales to ensure this moves forward, linked to portfolio changes agreed in Quarter 1 | Green | Data sharing protocol approved by all partners, including NHSO. New Anchor Strategy drafted, following engagement with staff and partners Strengthened approach to listening to and responding to patient and local community feedback - including BAME, LGBTQ+ and young people in Orkney | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadership Team and Assurence to Information Governance Committee Clear pieces of work are agreed with timescales to ensure this moves forward, linked to portfolio changes agreed in Quarter 1
2. Urgent and Unscheduled Care | 2.1 | 2023/24SG-0022 | Build on the communication successes to grow our impact. | New quarterly informal briefing session with members at Orkney Islands Council and NHS Orkney Board Strengthened relationships with local media briefings and meetings via Chair and CEO Strengthened internal communication from CEO and Executive Team | Informal briefing session with members at Orkney Islands Council and NHS Orkney Board Strengthened relationships with local media briefings and meetings via Chair and CEO | Informal briefing session with members at Orkney Islands Council and NHS Orkney Board Strengthened relationships with local media briefings and meetings via Chair and CEO | Informal briefing session with members at Orkney Islands Council and NHS Orkney Board Strengthened relationships with local media briefings and meetings via Chair and CEO | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about. Limited capacity in Communications. | To ensure equal focus between face-to-face and digital communications Review capacity required in the Communications Team | Green | Additional informal sessions with OIC have commenced - Exec to Exec and Board and Members CEO 100 Day Plan published - which focuses reconnecting with staff and the local community Quarterly media briefings with Chair and CEO have commenced Monthly all staff briefings in place and regular CEO and Executive Team comms in place | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about. Limited capacity in Communications. | To ensure equal focus between face-to-face and digital communications Review capacity required in the Communications Team | Green | Monthly meetings with Editor of The Orcadian and monthly touchpoint with Liam McArthur MSP for Orkney. Quarterly meetings with the Leader and CEO or Orkney Islands Council and CEO and Chair of NHS Orkney. | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about. Limited capacity in Communications. | To ensure equal focus between face-to-face and digital communications Review capacity required in the Communications Team
2. Urgent and Unscheduled Care | 2.2 | 2023/24QS-0029 | Review of Urgent and Unscheduled Care capacity to be taken forward to understand opportunity to extend the ability to 'schedule' unscheduled care to reduce self-presentation and prevent over-crowding | None Planned | Project team established to understand National principles to understand how they can best be applied to ensure that we maintain capacity at the front door to deal with emergency unscheduled presentations | Maintain embedded best practice with those identified additional staffing and pathways of care | Maintain and improve further where additionality is required or obstacles to success | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadership Team and Assurance to Finance and Performance Committee | Green | The DoNMAP and Chief Operating Officer Acute has scoped out opportunties and our regional links for flow navagation. | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadership Team and Assurance to Finance and Performance Committee | Green | Improvements have been recorded in the last quarter against the four hour targets. With the four hour target for both minors and admitted performance maintained at greater than 96% compliance. DoNMAP and Chief Operating Officer has agreed to facilitate with other Health Boards NHSO ED staff to be trained in triage to allow for further redirection and working is underway to commence OPAT. The Executive Lead is a member and fully engaged in the Flow Navagation Speciality Group. The Executive Lead has updated SLT, extended SLT, Board and IJB | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadership Team and Assurance to Finance and Performance Committee
2. Urgent and Unscheduled Care | 2.6 | 2023/24QS-0030 | Review of Rapid Assessment and Streaming to be undertaken to support early decision making and streaming to short stay pathways | Review of admission pathways from all parts of system - identification of gaps and additional resources to support early decision making | Identify respiratory resource within community to support - Is telemedicine in place - Is the Pharmacy capacity availale to support | Progress improvements related to the findings from Quarter 2 and embed best practice | Test changes and undertake lessons learned | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadsership Team and Assurance to Finance and Performance Committee | Red | Work was on hold due to urgent need to address urgent flow and capacity | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadsership Team and Assurance to Finance and Performance Committee | Amber | Identifcation required of system wide leadership and project management support to fully identify the capacity and resource requirements for implementation of telemedicine | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadsership Team and Assurance to Finance and Performance Committee
2. Urgent and Unscheduled Care | 2.7 | 2023/24QS-0031 | Review of Discharge Process to be undertaken through MDT approach | Discharge Planning is currently under review. A MDT approach across NHSO/IJB to understand blockers in system and consideration of current model. The Executive lead for Discharge Planning is Director of Acute. | Reestablish 6 essentials action approach for Discharge planning - embedding check, chase challenge prinicples. Ensuring early, on admission, discharge planning takes place | Maintain embedded best practice with those identified additional staffing and to support best pathways of care | Test changes and undertake lessons learned | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadsership Team and Assurance to Finance and Performance Committee | Green | Executive Leads discussed planning (next steps and challenges to success). Red/Amber/Green discharge document rolled out across inpatient areas. Weekly submission of those delayed transfers of care sent to CE NHSO and CE OIC for overview and system wide understanding. | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadsership Team and Assurance to Finance and Performance Committee | Green | Red/Amber/Green discharge pathways in use across inpatients, capturing MDT and pharmacological considerations that may impct on discharge planning. Focus remains on facilitating all discharges before noon. With current performance 12.5% on weekdays and 15% achieved on a weekend. Consideration of utilising a collection lounge and go live before winter is being progressed. | Other | Capacity to dedicate time to strategic work is limited | Reporting through Senior Leadsership Team and Assurance to Finance and Performance Committee
3. Mental Health | 3.1 | 2023/24SG-0036 | Improvement plan to ensure robust and timely data reporting for CAMHS including CAMHS PT | Work will be undertaken by the CAMHS team and Health Intelligence to patch and remedy anomalies in the CAMHS aggregate data | Maintain and embed the work completed in quarter 1 to ensure robust and accurate data reporting in relation to CAMHS aggregate data. Undertake GAP analysis of CAMHS CAPTND data | Maintain and embed the work completed in quarter 1 to ensure robust and accurate data reporting in relation to CAMHS aggregate data. Scope out how to deliver against the gap analysis findings. | Maintain and embed the work completed in quarter 1 to ensure robust and accurate data reporting in relation to CAMHS aggregate data Consider way forward and opportunities to introduce a fit for purpose electronic system, with capabilities to enhance the work that has been done during quarters 1, 2 and 3 | Other | Funding - There is no recurring or non-recurring funding to support a new system being introduced to support data reporting. Other - There is limited capacity with the eHealth function to support a project. The Mental Health team have no capacity to project manager and would result in the Service Manager's other duties being adversely affected. | Paper produced to articulate the need and would be progressed through the appropriate management and governance channels. | Green | Data being submitted meeting the Public Health Scotland deadline. Work has been undertaken and Orkney CAMHS CAPTND core data is now able to be submitted also. | Other | Funding - There is no recurring or non-recurring funding to support a new system being introduced to support data reporting. Other - There is limited capacity with the eHealth function to support a project. The Mental Health team have no capacity to project manager and would result in the Service Manager's other duties being adversely affected. | Paper produced to articulate the need and would be progressed through the appropriate management and governance channels. | Green | Data being submitted meeting the Public Health Scotland deadline. Work has been undertaken and Orkney CAMHS CAPTND core data is now able to be submitted also. | N/A | N/A | N/A
4. Planned Care | 4.4 | 2023/24SG-0039 | Waiting List Validation to be carried out through NECU | Agree the scope of the review and communication strategy | NECU to undertake the Waiting List validation | Receive feedback from NECU to understand current position. Address any obstacles to success and agree next steps | Report on impact of project and consider any additional opportunities to drive improvements | Other | Capacity for colleagues to support the additional work required to undertake review | Reporting will be through Senior Leadsership Team and onward to Finance and Performance Committee | Green | Scope of the review agreed - DPIA completed - Communication plan agreed | Other | Capacity for colleagues to support the additional work required to undertake review | Reporting will be through Senior Leadsership Team and onward to Finance and Performance Committee | Amber | NECU Admin Validation concluded and details shared with Clinical Leads to carry out Clinical Validation | Other | Capacity for colleagues to support the additional work required to undertake review | Reporting will be through Senior Leadsership Team and onward to Finance and Performance Committee
5. Cancer Care | 5.5 | 2023/24QS-0044 | Review opportunities to improve performance in relation to Cancer Care on Island | Development of action plan relating to reducing inequalities in screening for people with learning disabilities and people who have experienced intimate partner violence.1. Full adoption of CCE and theatre scheduling. 2. Include Psychological Therapies and Support Framework, as well as signosting to third sector services in all cancer pathways. Part of review of all clinical pathways and supporting SLAs. To start Q1 and be complete by Q4 | Collation of results from cancer screning inequalities work 1. Review ofcytosponge and qFIT for local adoption. 2. Start of implementation of ACRT with consideration of single point of contact model. | Development of inequalities screening plan relating to cancer screening work. Adoption of cytosponge and qFIT if appropriate. | 1. Review and implementation if appropriate of PIR 2. Full adoption of ACRT. 3. . Include Psychological Therapies and Support Framework, as well as signposting to third sector services in all cancer pathways. Part of review of all clinical pathways and supporting SLAs. To start Q1 and be complete by Q4 | Other | The most significant risk to delivering these objectives is capacity. This is capacity to undertake the necessary reviews, and capacity to then deliver any subsequent develomental workstreams. The risk is compounded by the absence of a dedicated medical lead for cancer within NHSO, and by fragility within the NHSO McMillan team. | 1. Engagement with CfSD to support NHSO in developing initiatives. 2. Funding to support 62-day pathways which will also free up some capacity for developmental work. 3. Consideration of agency requests to support the fragility already present. | Amber | Data collection in relation to inequalities project being collected. | Other | The most significant risk to delivering these objectives is capacity. This is capacity to undertake the necessary reviews, and capacity to then deliver any subsequent develomental workstreams. The risk is compounded by the absence of a dedicated medical lead for cancer within NHSO, and by fragility within the NHSO McMillan team. | 1. Engagement with CfSD to support NHSO in developing initiatives. 2. Funding to support 62-day pathways which will also free up some capacity for developmental work. 3. Consideration of agency requests to support the fragility already present. | Amber | Initial data collection completed re screening inequalties although limtied due to partner capacity. Action planning workshop being organised for early Nov. 62 day mprovement plan shared with cancer delivery group. | Other | The most significant risk to delivering these objectives is capacity. This is capacity to undertake the necessary reviews, and capacity to then deliver any subsequent develomental workstreams. The risk is compounded by the absence of a dedicated medical lead for cancer within NHSO, and by fragility within the NHSO McMillan team. | 1. Engagement with CfSD to support NHSO in developing initiatives. 2. Funding to support 62-day pathways which will also free up some capacity for developmental work. 3. Consideration of agency requests to support the fragility already present.
8. Workforce | 8.1 | 2023/24CU-0008 | Using the key engagement forums such as Area Partnership Forum, agree how we will enhance communication internally (across) and outside our organisation. | Enhanced communications in place internally and externally re: openness and transparency – including CEO blog, CEO and Executive team briefings and Executive Director comms Feeding back via internal comms how we are listening and acting on a more regular basis A 12-month plan for listening to and responding to feedback from staff | Improvements to iMatter score for staff feeling involved in decisions from 45% to >50% Overall experience of working at NHS Orkney to improve from 6.4 | Introduce strengthened health and wellbeing programme and reward and recognition programme for staff – with APF and wider team input To develop a new culture programme, which enables us to create a culture where staff feel valued, supported, listened to and safe to speak up | Test changes and undertake lessons learned | Wellbeing | Wellbeing - There is a risk that the ability to influence the staff experience score through 2023/24 iMatter following improvement programmes will be limited due to the timing | APF work plan under review Executive Team and CEO commitment to improving communications and engagement internally and externally (in personal objectives) | Green | 1. All staff monthly briefings commenced May 2023 - attended by CEO and Executive Directors 2. Fortnightly CEO blogs to all staff 3. Further to engagement with APF and wider staff, 5 organisational priorities launched in response to staff feedback for 23/24 with a strong focus on staff health and wellbeing, value, reward and recognition and involving staff in decision-making 4.Informal relationship meetings with key partners and stakeholders (including Exec-to-Exec with OIC, Leader of Council, Chair and CEO meetings and quarterly Members and NHSO Board briefing session, improved external communications, including more proactive comms on issues such as HDU and Macmillan 5. CEO 100-day plan on track for August publication 6. 2023/24 Staff Governance Action Plan, with priority areas, agreed | Other | Ensure consistency and year-round activity | APF work plan under review Executive Team and CEO commitment to improving communications and engagement internally and externally (in personal objectives) | Green | Launch 100-day CEO plan - setting out how we are responding to feedback (August 2023) Alignment of internal communications to strategic priorities (from end oif August) Agreeing APF workplan aligned to Plan on a Page Continued rhythm of monthly internal and external communications | Other | Ensure consistency and year-round activity | APF work plan under review Executive Team and CEO commitment to improving communications and engagement internally and externally (in personal objectives)
6. Health Inequalities | 2.3 | 2023/24CU-0009 | Ensure our Clinical Strategy informs our strategic decision-making process. | Delivery plan for Clinical Strategy and quarterly reporting to measure progress | Progress to be reported to SMT, Finance and Performance and Board | Progress to be reported to SMT, Finance and Performance and Board | Progress to be reported to SMT, Finance and Performance and Board | Finance | Financial envelope available to support delivery of Clinical Strategy aspirations | Escalation route for oversight of risks and issues which could impact on deliverable to ensure delivery Measuring progress on a bi-annual basis against clinical strategy action plan will help to inform level of tolerable risk across services | Green | Paper presented to Board in June summarising way forward in terms of reporting against the action | Finance | Financial envelope available to support delivery of Clinical Strategy aspirations | Escalation route for oversight of risks and issues which could impact on deliverable to ensure delivery Measuring progress on a bi-annual basis against clinical strategy action plan will help to inform level of tolerable risk across services | Amber | Delivery Plan progress to come to October 2023 Board and 6-monthly thereafter | Finance | Financial envelope available to support delivery of Clinical Strategy aspirations | Escalation route for oversight of risks and issues which could impact on deliverable to ensure delivery Measuring progress on a bi-annual basis against clinical strategy action plan will help to inform level of tolerable risk across services
8. Workforce | 6.1 | 2023/24SU-0024 | Support the organisation to achieve a sustainable future by using the Clinical Strategy, Workforce Plan and Financial Sustainability Plans to inform and shape our decisions. | Create a Planning Hub to support a collaborative approach Production of Annual Delivery Plan and Medium-Term Plan | Undertake lessons learned from Planning approach for 2023/24 | Commence Planning process for 2024/25 and beyond | Continue to carry out reviews to ensure that planning process captures changes in demand and remains fit for purpose | None Identified | N/A | Reporting through Senior Leadership Team , Finance and Performance and Board | Green | Draft documentation has been started to describe the benefits of a Planning Hub approach (Terms of Reference, Key Stakeholders and Planning Cycle) to be shared with SLT for approval Annual Delivery Plan submitted to SG awaiting formal feedback letter. Engagement sessions completed for Medium-Term Plan and draft being produced | None Identified | None Identified | Reporting through Senior Leadership Team , Finance and Performance and Board | Amber | To enhance the scope of the group to ensure the action is progressed and ultimately delivered, membership of the group to include Public Health (Health Improvement) and Estates and Facililties (Sustainability). Opportunities to test change have been agreed which includes Anchor Strategy and Healthcare Staffing Act. The group will look to support services in relation to creation and delivery of plans. | None Identified | N/A | Reporting through Senior Leadership Team , Finance and Performance and Board
7. Innovation Adoption | 6.1 | 2023/24SU-0026 | Continue the progress of the multi-year financial recovery plan by getting ownership across the organisation. | FSO workplan to be approved by EMT/SMT | Establish Financial Recovery Board where reported savings are reviewed, monitored and appropriate action taken | Financial Recovery Board to meet with remit of reviewing and monitoring reported savings and ensuring appropriate action taken | updates to be received from the Energy Efficiency Group into Sustainability Steering Group and onward to Finance and Performance Committee. | Other | Other - There is risk that the deliverable will not be achieved if Executive Directors do not have the capacity to take forward the projects within their remit | Oversight of the Financial Recovery Plan will be through SMT and onward to Finance and Performance | Amber | First round of Confirm and Challenge sessions took place. Grip and Control Board established. Executive Leads have agreed key schemes which FSO will support | Other | Other - There is risk that the deliverable will not be achieved if Executive Directors do not have the capacity to take forward the projects within their remit | Oversight of the Financial Recovery Plan will be through SMT and onward to Finance and Performance | Red | The FSO team continues to provide support to the Executive Sponsors to progress those projects which have been identified and will support delivery of the financial recovery plan Senior Leadership team and Board both met in September to approve 6 out of 8 additional schemes in response to the worsening financial position which is currently forecast at £5.9m. Grip and control Board continues to meet to check, challenge and foster savings opportunities across the Board. | Other | Other - There is risk that the deliverable will not be achieved if Executive Directors do not have the capacity to take forward the projects within their remit | Oversight of the Financial Recovery Plan will be through SMT and onward to Finance and Performance
7. Innovation Adoption | 2.1 | 2023/24QS-0012 | Use latest guidance to ensure meaningful patient feedback mechanisms are in place which demonstrate that we listen, act and learn. | Consider use of Care Opinion to capture patient experience/feedback in a more rounded way | Paper to be presented to NHSO Board in Aug for discussion and plan future activity in this area. | Take forward plan agreed by Board | Continue to embed plan | Finance | There may be a cost to further work in this area which is not yet captured within the current NHSO budget. | Attempt to minimise cost implication of any new process | Red | Patient Experience Officer and Patient representatives invited to participate in the Pain Serivce review project | Capacity | Capacity within existing team. Potential that patient feedback is received via areas outwith Patient Experience and not recorded or co-ordinated | Develop mechanisms to capture patient experience across the entire service including systems within the Clinical Admin team | Red | Paper to Board in August 2023 with new approach to patient experience reporting agreed New Interim Medical Director commenced in post September 2023 who will lead on Clinical Governance Care Opinion in place | Capacity | Capacity within existing team. Potential that patient feedback is received via areas outwith Patient Experience and not recorded or co-ordinated | Develop mechanisms to capture patient experience across the entire service including systems within the Clinical Admin team
7. Innovation Adoption | 7.2 | 2023/24QS-0015 | Continue to embed the Serious Adverse Events and learning form incidents process. | Training request submitted by Clinical Governance to train 12 colleagues on significant adverse events. This course will allow colleagues when trained to participate in reviews to support the wider organisation when things don't go as planned | None Planned | None Planned | 12 colleagues to have undertaken training through NHS Lanarkshire | Finance | Non-Recurring Funding - Funding has been identified for 2023/24 but if this is required on an ongoing basis recurring funding will have to be identified | Going forward training will be identified in line with the workforce/delivery planning process, to ensure appropriate prioritsation | Amber | A system has been developed to embed tracking of identifiied SAER learning as part of the Quality Forum Terms of Reference | Other | If NHSO fails to learn lessons from SAERs that mistakes will be repeated and patients put at risk | By reviewing the action log on monthly basis necessary actions can be monitored and themes identified | Green | Continue to embed system developed in Quarter 1 | Other | If NHSO fails to learn lessons from SAERs that mistakes will be repeated and patients put at risk | By reviewing the action log on monthly basis necessary actions can be monitored and themes identified
7. Innovation Adoption | 7.1 | 2023/24QS-0016 | Explore where single points of failure exist what can practically be done to address these. | Explore where single points of failure exist what can practically be done to address these. | A review of all clinical pathways, supporting SLAs, and associated data requirements will start in Q1 and be complete by Q4. This will help to identify single points of failure and areas of service fragility which can then be addressed. | None Planned | A review of all clinical pathways, supporting SLAs, and associated data requirements will start in Q1 and be complete by Q4. This will help to identify single points of failure and areas of service fragility which can then be addressed. | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent developmental workstreams. | 1. Clear project plan with clear deliverables. 2. Seek external support as required. | Amber | Review of clinical pathways and SLAs has commenced. Information being gathered via weekly waiting times meeting. | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent developmental workstreams. | 1. Clear project plan with clear deliverables. 2. Seek external support as required. | Amber | Review of clinical pathways and SLAs continued to identify and support Fragile Service review. Information being gathered via weekly waiting times meeting. | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent developmental workstreams. | 1. Clear project plan with clear deliverables. 2. Seek external support as required.
7. Innovation Adoption | 7.1 | 2023/24QS-0017 | Ensure learning from the HSE visit is acted on and risk management is firmly embedded with visible leadership present in all teams. | Refreshed Risk Management Strategy and Risk Management Forum Terms of Reference to be produced and approval through RMF and Audit and Risk Committee Oversight of Risk Management to be reported to SMT, Audit and Risk and the Board. Risk Owners and Handlers to meet with the Clinical Governance and Risk Facilitator on a pre-agreed timeline to ensure risks are captured and updated at all times | Risk Management Strategy to be approved by Board and appropriate policy updates progressed following approval Oversight of Risk Management to be reported to SMT, Audit and Risk and the Board. Risk Owners and Handlers to meet with the Clinical Governance and Risk Facilitator on a pre-agreed timeline to ensure risks are captured and updated at all times | Oversight of Risk Management to be reported to SMT, Audit and Risk and the Board. Risk Owners and Handlers to meet with the Clinical Governance and Risk Facilitator on a pre-agreed timeline to ensure risks are captured and updated at all times | Oversight of Risk Management to be reported to SMT, Audit and Risk and the Board. Risk Owners and Handlers to meet with the Clinical Governance and Risk Facilitator on a pre-agreed timeline to ensure risks are captured and updated at all times As part of the Annual Accounts process a summary of Risk to be produced | Absence | Absence - The capacity within the organisation is 1 WTE to support the regular meetings and production of key reporting. If this individual was absent for a prolonged period of time this would impact what could be achieved | If absence becomes a risk, NHSO would need to look for external support to provide the minimum capacity required to provide the support and assurance | Amber | The Interim Director of Human Resources has completed the relevant activities linked to the HSE and this has been signed off at the Board in 2022. Activities aligned to the HSE outwith training sit under the relevant Exec Directors, Mental Health DH&SC/Risk - MD/Patient Notes - DNMAHP&Acute | Absence | Absence - The capacity within the organisation is 1 WTE to support the regular meetings and production of key reporting. If this individual was absent for a prolonged period of time this would impact what could be achieved | If absence becomes a risk, NHSO would need to look for external support to provide the minimum capacity required to provide the support and assurance | Amber | Review of Tier 1 and Tier 2 Risk Registers undertaken by Chief Executive and Planning, Performance and Risk Manager. Risk owner/handlers to review findings of review | Capacity | Clinical Governance and Risk Facilliator left organisation creating a gap in terms of reporting and updating | Gap being filled by Planning, Performance and Risk Manager short term
8. Workforce | 8.1 | 2023/24WF-0001 | Acknowledge the range of pressures our workforce face personally and professionally and maximise support for them through a range of actions. | First NHS Orkney Staff Stress Survey (tool is made up of a framework of HSE Stress Management Standards around which a set of questions are based.) to be presented to Area Partnership Forum for approval of roll-out during 2023/24 | Planning phase for roll-out, including considerations around potential risks and issues impacting the outcomes of the tool | Issue the NHS Orkney Stress Survey to all Board and IJB colleagues | Survey responses to be reviewed and discussed through Occupational Health, Safety and Wellbeing Commmittee. Based on responses to the survey, an Organisational Stress Risk Assessment will be produced | Other | Capacity - for staff to undertake the survey Engagement - Staff willingness to engage with the tool Expectations - those completing the tool anticipating immediate fix | The controls will be captured in the planning phase during quarter 2, prior to issuing tool during Quarter 3 | Green | Signed off by SGC May2023. Questions defined for use. Roll out plan is underway and will be aligned to the commencement of new Health and Safety colleagues joining in August. Bid is developed with appropiate supporting documentation. Currently with CEO prior to going to the Endowment Committee. | Capacity Engagement Expectations | Capacity - for staff to undertake the survey Engagement - Staff willingness to engage with the tool Expectations - those completing the tool anticipating immediate fix | The controls will be captured in the planning phase during quarter 2, prior to issuing tool during Quarter 3 | Green | 1. Been to APF and Staff Governance Committee and fully approved. Stress Survey Tool provided to NHS Orkney and this process is being supported by Public Health. Survey will be open from the 13th November to 23rd December. 2. Bid developed and presented to Endowments Committee 20th July - approved. Wellbeing event underway w/c 25th September. Out to recruit for Wellbeing Coordinator post. Employee Assistance Programme launched 26th September. Team Orkney Awards planning udnerway via Wellbeing Committee. Interm Director of HR raised at CLT on 26th September that colleagues on the Wellbeing Committee need to be more participative and engaged in delivery. | Capacity Engagement Expectations | Capacity - for staff to undertake the survey Engagement - Staff willingness to engage with the tool Expectations - those completing the tool anticipating immediate fix | The controls will be captured in the planning phase during quarter 2, prior to issuing tool during Quarter 3
8. Workforce | 8.1 | 2023/24WF-0002 | Invest in leadership and staff development. | Define the purpose, and scope of a Leadership Development Programme in partnership with NHS Shetland. | Agree the purpose, and scope of a Leadership Development Programme in partnership with NHS Shetland, by end of August 2023. Trial the Leadership Development Programme offering from September 2023 for new starts. | Consider feedback/learning from the trial programme. | Formalise programme by February 2024. | Other | Funding not yet agreed - the quality and delivery could be impacted if the minimum funding is not agreed to support the programme progressing. Training, Development and Skills - this is a new programme that will require focus and capacity through the People and Culture Team | We will continue to review the focus of the organisations and balance the needs to deliver, this may mean that other work is stopped based on a prioritsation of needs | Amber | QI fundamentals training organised for FSO and wider staff in project management roles (July 2023) 1. work is currently undeway in the collaboration of the delivery -update to APF - August 2. not identified as a need as part of the signed off training plan ior activity linked to the Staff Governance Action Plan under skills - as a new addition and request we will undertake a TNA - Q2 - what has been delivered to support upskilling staff via the Flexible Workforce Development Fund SVQ 2 - Business & Administrationx 1/SVQ 3 - Business & Administration x2/ SVQ 2 - Social Services & Healthcarex 1/ ECDL 1 (Essentials) x 1/CMI Level 6 First Line Management x 1/Project Management x12/Minuting of meetingsx 6 | Funding not yet agreed Training, Development and Skills | Funding not yet agreed - the quality and delivery could be impacted if the minimum funding is not agreed to support the programme progressing. Training, Development and Skills - this is a new programme that will require focus and capacity through the People and Culture Team | We will continue to review the focus of the organisations and balance the needs to deliver, this may mean that other work is stopped based on a prioritsation of needs | Amber | Leadership Forum with Orkney Islands Council (Sept 2023) for service managers and senior teams. Summer 2023 - Quality Improvement training for a cohort of staff Commencement of quarterly leadership talks - starting with Brian Dolan webinar 1. Capacity ensured to look at programme and align to relevant bandings. Draft framework December 2023. 2. Ray Knox to be procured to deliver bespoke training linked to budget. Joint Leadership Session with OIC 27th September. | Funding not yet agreed Training, Development and Skills | Funding not yet agreed - the quality and delivery could be impacted if the minimum funding is not agreed to support the programme progressing. Training, Development and Skills - this is a new programme that will require focus and capacity through the People and Culture Team | We will continue to review the focus of the organisations and balance the needs to deliver, this may mean that other work is stopped based on a prioritsation of needs
8. Workforce | 8.1 | 2023/24WF-0003 | Use the Healthcare Staffing Act to enhance and shape our actions in relation to staffing. | Re-establishment of NHSO HCSA Programme Board to drive preparation for implementation 1 Apr 24 Testing for guidance chapters - C6 : Adequate Time for clinical leaders | National 3Cs staffing level tool(s) run(s) * Community Nursing – East/West Mainland community nursing teams, GP isles nurses, health visitors, school nurses w/c 5 Jun & w/c 4 Sep 23 for 2-weeks Testing for guidance chapters - C9 : Staff Training and Consultation | National 3Cs staffing level tool(s) run(s) *Clinical Nurse Specialists – Long term conditions, cancer palliative, emergency nurse practitioners, infection prevention & control, public health, including vaccination team(s) w/c 16 Oct 23 & w/c 22 Jan 24 Testing for guidance chapters - C7 : Duty to Seek Clinical Advice on Staffing | Completion of HIS HSP Board self-assessment template *NHSO Q4 FY 2022/23 submitted to SG (x11 Duties – x8 graded red, x3 graded Amber) Future proof governance & familiarisation, education & training post 31 Mar 24 when SG funding to Boards to support implementation preparation ceases | Other | Limited assurance around governance structure, systems and processes in place with relevant leadershup to demonstrate compliance in advance of enactment | Programme Board Established to receive oversight - Reporting onward to Senior Leadership Team and Staff Governance Committee | Amber | Progression maed in relation to - 12IB – Duty to ensure appropriate staffing: agency worker 12IC – Duty to have real-time staffing assessment in place 12ID – Duty to have risk escalation process in place 12IE – Duty to have arrangements to address severe and recurrent risks 12IF – Duty to seek clinical advice on staffing 12II – Duty to ensure appropriate staffing: training of staff 12IJ – Duty to follow the common staffing method "12IL – Training an Consultation of Staff – Common Staffing Method (This specifically relates to Types of Healthcare & Employees Section 121K (1))" 12IM – Reporting on Staffing | Other | Limited assurance around governance structure, systems and processes in place with relevant leadershup to demonstrate compliance in advance of enactment | Programme Board Established to receive oversight - Reporting onward to Senior Leadership Team and Staff Governance Committee | Amber | Q2 update to be produced alongside Q3 | Other | Limited assurance around governance structure, systems and processes in place with relevant leadershup to demonstrate compliance in advance of enactment | Programme Board Established to receive oversight - Reporting onward to Senior Leadership Team and Staff Governance Committee
8. Workforce | 8.1 | 2023/24WF-0004 | Support teams to review their roles, responsibilities and engage with others to promote shared learning and collaboration. | A review of Executive portfolios will be completed with Objectives set for each Director | Clear objectives to be set for Senior Management Team colleagues and their services which align to Strategic Priorities for the organisation | Review roles and repsonsibilties for wider team considering the outcomes of the establishment review. |  | None Identified | N/A | Reporting through Senior Leadership Team, Remuneration Committee, Staff Governance Committee and Board | Green | 1.Completed and shared with the organsation. 2. Completed and signed off by Remuneration Committee June New Executive Team portfolios launched 3 July 2023 Executive Director personal objectives set for 23/24 | None identified | None identified | Reporting through Senior Leadership Team, Remuneration Committee, Staff Governance Committee and Board | Green | Personal objectives for full Executive Team agreed Strengthened focus on multi-discplinary team learning and working Clarity with Senior Leadershiup Team and extended Senior Leadership Team about leadership responsibities, roles and expectations re: behaviours, accountability and ownership of issues Complete - Interim collegues objectives being set and will go before Remuneration Committee within 4 weeks of commencement | N/A | None identified | Reporting through Senior Leadership Team, Remuneration Committee, Staff Governance Committee and Board
8. Workforce | 8.1 | 2023/24WF-0005 | Use the Workforce Plan to support succession planning. | Agree the scope and core project members for a establishment review which includes succession planning with the scope of the review. | Establishment review considering the current funded establishment against the current actual establishment (including temporary staffing models) continuous support and drive for graduate apprenticeships | Consider the outcomes of establishment financial review against the critical service needs with an aim to identify succession planning requirements and actions. Standardise and develop staff and manager appraisal training with an aim to support identifying clear progression routes and succession planning. Roll out by December 2023. | Training requests aligned to succession planning to be submitted by all services in Quarter 4. The Leadership Development Programme will be available for consideration through this process. The programme will include training solutions to support succession planning | Other | Funding not yet agreed - There is no agreed funding for succession planning the scale of the problem/opportunity is currently unknown Training, Development and Skills - There is a risk that the required training is not available locally and this may impact on the ability for colleagues to undertake the training which would allow them the opportutnity to develop Recruitment - NHSO can be challenged in attracting candidates due to limitations for personal development due to the service delivery model | Organisation wide Training Plan to be launched, which considers all managers requests to enable succession planning. Continue to take personalised approach for recruitment campaigns. | Amber | 1. To be discussed at CLT 2. HR completed staff under contract work. Finance currently reviewing budgeted staff Succession Planning commenced with Executive Team (July 2023) Phase 1 of the Estabishment Review | Finance | 2. Risk that more colleagues will hold contracts of employment than allocated funding | 1. Finance should be completed end of July - HR will then review and have an initial conversation with Exec manager. Systems will then be updated to accurately reflect contractual establishment and CLT/SLT aware of actual true finances for staffing in post vs historic budgeted in post - 2. Vacancy Control Panel via FSO | Amber | Executive Team session on succession planning completed Establishment with Exec Directors to review and review of next steps with CEO, DoF , Interim DoHR and Head of P&C w/c 2nd October. Proposed succession planning process going to Staff Governance Committee November 2023. Continued support for graduate apprenticeships planning with Herriot Watt University for 2024 to provide local education delivery model. | Finance | 2. Risk that more colleagues will hold contracts of employment than allocated funding | 1. Finance should be completed end of July - HR will then review and have an initial conversation with Exec manager. Systems will then be updated to accurately reflect contractual establishment and CLT/SLT aware of actual true finances for staffing in post vs historic budgeted in post - 2. Vacancy Control Panel via FSO
8. Workforce | 8.1 | 2023/24WF-0006 | Explore how to strengthen our induction and orientation process. | New induction to be implemented in April 2023 following improvement project led by People and Culture but with representation from across NHSO. | Formal review of feedback from new start colleagues and line managers to ensure further improvements are captured appropriately in relation to onboarding and induction. | Formal review from participants and trainers to measure the outcomes of the aligned training induction weeks have been achieved. | Make any alternations and feedback based on feedback received throughout the year taking into consideration any previous changes which have been implemented. | Absence | Absence - Capacity in the team can often mean that the organisation has 1 subject matter expert. In the event that the subject matter expert is absent from work for a prolonged period of time ability to deliver could be impacted | If absence becomes a risk, NHSO would need to look for external support to provide statutory and mandatory training to colleagues as part of their induction and everyday learning | Green | Completed - Induction commenced as agreed and signed off by SGC CEO attending induction to meet all new starters (from July 2023) | Absence | Absence - Capacity in the team can often mean that the organisation has 1 subject matter expert. In the event that the subject matter expert is absent from work for a prolonged period of time ability to deliver could be impacted | If absence becomes a risk, NHSO would need to look for external support to provide statutory and mandatory training to colleagues as part of their induction and everyday learning | Green | CEO attends every monthly staff induction to welcome new starters and share key messages about: strategic objectives, vision, values Completed evaluation of corporate induction and now looking at induction at local departmental level and also for locum, consultant and manager level. | Absence | Absence - Capacity in the team can often mean that the organisation has 1 subject matter expert. In the event that the subject matter expert is absent from work for a prolonged period of time ability to deliver could be impacted | If absence becomes a risk, NHSO would need to look for external support to provide statutory and mandatory training to colleagues as part of their induction and everyday learning
8. Workforce | 8.1 | 2023/24WF-0007 | Build on learning from Covid, ensure wellbeing and resilience is central to our decision-making processes. | Empowering staff to lead change in their local areas and implement their own ideas for improvement | Empowering staff to lead change in their local areas and implement their own ideas for improvement | Continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge | Continued focus on creating a continuous improvement culture, by upskilling staff with quality improvement skills and knowledge | Other | Capturing the data and data quality and defining KPIs on how staff feel | imatter board report and executive engagement with teams | Amber | 1. to discuss at SLT - August around how we create small steps of change - review how many NHS Orkney staff have attended NHSO and NHSS SIFS course and who have improvement skills - 2. completion of imatter questionaire/managers to support action planning q2 exploration conversation around the use of 'Trickle'- employee experience platform Improvement project underway in Physiotherapy Services with a focus on leadership, culture, data and service improvement Strengthened health and wellbeing programme in place, including a new Employee Assistance Helpline, and a new reward and recognition programme | Other | Capturing the data and data quality and defining KPIs on how staff feel | imatter board report and executive engagement with teams | Amber | New strengthened health and wellbeing programme for staff - including new Employee Assistance Programme Successful staff health and wellbeing 2-day event, with support from partners Priorities communicated and shared across the organisation, departments are undertaking their action plan activities. iMatter action planning has increased significantly from 2022. We elected not to use trickle due to cost, will see further use of communication calendar of wellbeing and engagement after the appointment of Wellbeing Coordinator. | Other | Capturing the data and data quality and defining KPIs on how staff feel | imatter board report and executive engagement with teams
8. Workforce | 8.1 | 2023/24CU-0010 | Explore development opportunities for staff to support enhanced communication skills. | iMatter questionnaires issued to allow managers to receive feedback from their teams. | Action planning phase of iMatter will allow teams to create key focussed areas to enhance their teams performance and communication. | Personal development plans for staff via appraisals To create a menu of development and training opportunities accessible to staff Improvements in iMatter score for staff feeling appropriately trained and developed (from 54% to >60%) Feedback to be collated based on reponses received across the organisation, to allow for clear actions to be agreed and progressed | Continue to monitor and seek feedback, implement any further changes as required | Wellbeing | Wellbeing - There is a risk that colleagues could react to the discussions differently depending on their personality type. | This will be captured in the planning phase during quarter 2 and support will be available through a number of colleagues (for example Occ Health, Line Manager, People and Culture Team) | Amber | Cascaded via Exec teams re appraisals and PDPs - training added around minuting meeting and chairing skills | Other | No organisational TNA - See activity taking place under workforce re TNA | This will be captured in the planning phase during quarter 2 and support will be available through a number of colleagues (for example Occ Health, Line Manager, People and Culture Team) | Amber | 1. Capacity ensured to look at programme and align to relevant bandings. Draft framework December 2023. 2. Ray Knox to be procured to deliver bespoke training linked to budget. Joint Leadership Session with OIC 27th september 3. imatter action plan updates to be regularly reported to SGC | Other | No organisational TNA - See activity taking place under workforce re TNA | This will be captured in the planning phase during quarter 2 and support will be available through a number of colleagues (for example Occ Health, Line Manager, People and Culture Team)
8. Workforce | 8.1 | 2023/24CU-0011 | Work to ensure governance work is visible and meaningful to staff. | Clear communications to staff about how decisions are made at NHS Orkney and timely communications about key decisions | New Senior Leadership Team from 1 July, which is clinically-led, and in response to staff feedback re: how decisions are made Review of operational governance | Review of operational governance | Improvements in iMatter scores for staff feeling well informed (from 63% to >70%) | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | A balance of face-to-face and digital communications to maximise reach to staff Review being undertaken by NHSO Chair to which will review communication in relation to Governance Committees | Green | New Senior Leadership Team launched 3 July 2023 with new terms of reference and this was clearly communicated across the organisation. A communication is issued after every SLT to staff to update on key discussions and decisions. August 2023 - review of wider operational governance commences so we can ensure this is clear, we minimise duplication and we maximise staff input into decision-making in the organisation. A Committee Chair Communication Working Group is in place to improve communication from the Board Committees back into the organisation | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | A balance of face-to-face and digital communications to maximise reach to staff Review being undertaken by NHSO Chair to which will review communication in relation to Governance Committees | Green | New Senior Leadership Team meeting launched July 2023 (fortnightly meetings to ensure faster and clinically led decision-making in response to staff feedback) After every SLT an all staff communications is issued summarising key discussion points, areas for concern and key work underway Extended SLT met for the first time in October 2023 - to focus on taking forward startegic matters, with a focus on winter and escalation plans and transformational ideas re: financial improvement. Board development programme with Royal College of Physicians Edinburgh continues with development on new Board Assurance Framework to commence next quarter | Other | Inadequate internal communications channels and over-reliance on digital communications means changes are not seen or widely known about | A balance of face-to-face and digital communications to maximise reach to staff Review being undertaken by NHSO Chair to which will review communication in relation to Governance Committees
8. Workforce | 8.1 | 2023/24QS-0013 | Empower staff to make changes to improve care. | Regular listening session and drop-in events for staff | Operational governance review | Review of operational governance | Review of operational governance | Other | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture iMatters action plans and Reporting through Senior Leadership Team and Board | Green | DoNMAHP IP2 and MacMillan listening session, to discuss reintroduce of symptom control as a model of care in MacMillan.Clinical Nurse Managers have completed induction including spending time with colleagues in NHSH, both now have identified portfolios to lead | Other | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture iMatters action plans and Reporting through Senior Leadership Team and Board | Green | Wider engagement with Medical and Clinical colleagues to support system challenges for example Pain Service Review. | Other | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture iMatters action plans and Reporting through Senior Leadership Team and Board
8. Workforce | 8.1 | 2023/24QS-0014 | Support staff to learn when things don’t go as planned. | Training Plan to be approved, based on an organisation training requests for 2023/24, which includes a request for training from Clinical Governance to train 12 colleagues on significant adverse events. This course will allow colleagues when trained to participate in reviews to support the wider organisation when things don't go as planned | None Planned | None Planned | 12 colleagues to have undertaken training through NHS Lanarkshire | Non-Recurring Funding | Non-Recurring Funding - Funding has been identified for 2023/24 but if this is required on an ongoing basis recurring funding will have to be identified | Going forward training will be identified in line with the workforce/delivery planning process, to ensure appropriate prioritisation | Green | Increased in the number of individuals trained as SAER investigators. This means that staff are supported appropriately through the investigation process | Non-Recurring Funding | Non-Recurring Funding - Funding has been identified for 2023/24 but if this is required on an ongoing basis recurring funding will have to be identified | Going forward training will be identified in line with the workforce/delivery planning process, to ensure appropriate prioritisation | Green | Increased in the number of individuals trained as SAER investigators. This means that staff are supported appropriately through the investigation process | Non-Recurring Funding | Non-Recurring Funding - Funding has been identified for 2023/24 but if this is required on an ongoing basis recurring funding will have to be identified | Going forward training will be identified in line with the workforce/delivery planning process, to ensure appropriate prioritisation
8. Workforce | 8.1 | 2023/24SG-0019 | Empower staff to make decisions in a collaborative, open and transparent way. | Regular listening session and drop-in events for staff | Operational governance review | Review of operational governance | Review of operational governance | Other | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture | Amber | Monthly listening and drop in events for all staff | Other | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture | Amber | iMatter results show NHSO is an outlier for this question nationally and that there is more to be done. Efforts are being made to better involve staff in decision-making and the second area where we need to improve is staff having confidence that when they fdeedback or speak up that changes and improvements will happen | Other | Change and empowerment requires culture change and trust and we are in the early stages of our journey - it will take time | Continued focus on leading with kindness, living our values, openess and transparency and honest conversations, strong internal communications and listening to and responding to staff, as well as following through on actions and closing the loop - all of which if done consistently will begin to change the culture
8. Workforce | 8.1 | 2023/24SG-0023 | Strengthen training for leaders and managers to allow decision-making to take place at an appropriate level. | None Planned | Improve support for managers at induction stage. Create clear operating procedures to explain what is required from managers when it comes to 1-2-1s, valuing staff, supporting staff development, keeping staff well-informed and holding annual appraisals | Monitor and measure impact of change | Consider impact of change and additional areas for improvement | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent develomental workstreams. | Reporting will be through Senior Leadership Team and onward to Staff Governance Committee | Amber | To commence conversations around elements of management skills eg finance and budgetary management for non finance managers | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent develomental workstreams. | Reporting will be through Senior Leadership Team and onward to Staff Governance Committee | Amber | QI training session for staff held (Summer 2023) Joint Leadership Forum for Orkney Islands Coucnil and NHSO (September 2023) Leadership session with Brian Dolan (endPJparalysis) - September 2023 | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent develomental workstreams. | Reporting will be through Senior Leadership Team and onward to Staff Governance Committee
9. Digital | 9.2 | 2023/24SG-0037 | Work to transition GP colleagues to a single system is being progressed through IT reprovisioning project | None Planned | None Planned | Working Group to be established | Work to be progressed with local GP practices | Other | Other (Capacity) - NHSO Primary Care does not have a full compliment of IM&T facilitators to run their systems. Other (Georgaphical Location) - An issue may occur if the cloud based system does not perform well over high latency links as is currently the case. Training, Development and Skills - Offlining / migration of the GPs will put extra pressure on the system | The Head of Primary Care is currently looking at resource plans for the facilitation. | Green | None planned | N/A | N/A | N/A | Amber | Initial scoping exercise underway. Working group formed and meetings in diary. | Other (Capacity) - NHSO Primary Care does not have a full compliment of IM&T facilitators to run their systems. Other (Georgaphical Location) - An issue may occur if the cloud based system does not perform well over high latency links as is currently the case. Training, Development and Skills - Offlining / migration of the GPs will put extra pressure on the system. Finance needs to sourced to deliver the project | Project manager needs to be identified to review work to date and costings that will need to found to fund the project. | Working group established
2. Urgent and Unscheduled Care | 6.4 | 2023/24CU-0032 | Establish and embed the Women's Health Lead to drive change, share best practice and innovation, and delivery of the actions in the Women's Health Plan | Lead to be identified | Create action plan to address the requirements, with objectives and timelines to measure success | Progress actions, ensuring reporting against objectives | Test changes and undertake lessons learned | None Identified | N/A | Reporting through Senior Leadership Team and Area Partnerhip Forum | Green | Lead identified - Lead Midwife/Interim Deputy Director of Nursing | None Identified | N/A | Reporting through Senior Leadership Team and Area Partnerhip Forum | Amber | Meeting with National Lead - Work progressing with action plan build | None Identified | N/A | Reporting through Senior Leadership Team and Area Partnerhip Forum
6. Health Inequalities | 6.1 | 2023/24SG-0033 | NHS Orkney are using Marmot principle as a framework to underpin the work we do with partners to address inequalities in Orkney | None Planned | Provide Marmott guidance to public health staff. | Review current work plan to ensure all Marmott prinicples have been considered | Provide specialist public health knowledge relating to Marmott principles to partners | Workforce | Potential lack of understanding of Marmot Prinicples as driver within Public Health staff | Will re-frame current plan which is related to 6 public health priorities to Marmot principles and address any gaps. | Amber | Beginning to explore implementation | Workforce-training and skills development | Potential lack of understanding of Marmot Prinicples as driver within Public Health staff | Will re-frame current plan which is related to 6 public health priorities to Marmot principles and address any gaps. | Amber | Marmott prinicples embedded as assessment criteria for Community benefits bids for Orkney through Community Benefits Portal. | Workforce-training and skills development | Potential lack of understanding of Marmot Prinicples as driver within Public Health staff | Will re-frame current plan which is related to 6 public health priorities to Marmot principles and address any gaps.
6. Health Inequalities | 6.1 | 2023/24SG-0034 | The Orkney child poverty strategy and implementation plan are being progressed with our community planning partners | None Planned | Provide specialist public health input to Cost of Living Deliver Group and Money Counts project to progress actions | Provide specialist public health input to Cost of Living Deliver Group and Money Counts project to progress actions including training plan | Provide specialist public health input to Cost of Living Deliver Group and deliver training relating to Money Counts project to progress actions | Workforce | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Contributing through participation in the Cost of Living Taskforce | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Contributing through participation in the Cost of Living Taskforce and Money Matters project. Work ongoing in NHS Orkney to support staff to use the money matters referral pathway once released. 7 | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.1 | 2023/24CU-0035 | Work is underway with Orkney Islands Council to develop an Orkney Fuel Poverty Strategy working with the Orkney Cost of Living (CoL) Task Force. A CoL action plan has been developed to mitigate the impact of the CoL crisis for the population of Orkeny and improve living standards. Within the NHS specific actions are being implemented to support our staff. We are providing training for staff across the health and social care partnership relating to financial inclusion and developing a financial inclusion pathway to be used by frontline staff. | None Planned | Provide public health specialist input initial development phase of strategy ensuring taking account of public health principles, Stakeholder collaboration to implement NHS Orkney Cost of Living Crisis plan achieved | Provide public health specialist input into the development phase of strategy ensuring taking account of public health principles, NHS Orkney Cost of Living Crisis plan achieved | Completion of Fuel Poverty Strategy, implementation of the financial inclusion pathways | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Cost of Living Plan received by APF and ACF. | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Contributing through participation in the Cost of Living Taskforce and work ongoing to progress Cost of Living Plan | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.1 | 2023/24QS-0038 | In line wiht the Equality Evidence Strategy 2023 to 2025, we are working in partnership with NHS Shetland to deliver a project to improve access to adult screening programmes for people with a learning disability. | None Planned | Completion of data collection | Formation and sharing of action plan | Test changes and undertake lessons learned | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Amber | Data collection from participants in progress | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Amber | Data collected but not reported due to staff absence in partner board | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.1 | 2023/24QS-0040 | To support the implementation of the Women's Health Plan and improve access to national adult screening programmes for women who have experienced initmate partner violence, we are working in partnership with Women's Aid and Orkney Rape and Sexual Assault Service learn from women's lived experience and develop an action plan to remove barriers and promote access to screening for women. | None Planned | Completion of data collection | Formation and sharing of action plan | Test changes and undertake lessons learned | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Data collection from participants in progress | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Initial data collection completed although limtied due to partner capacity. Action planning workshop being organised for early Nov. | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.1 | 2023/24QS-0041 | We are developing smoking cessation staff with specialist skills to support women during pregnancy | Staff member trained to support women who smoke in pregnancy to stop smoking | Trained staff to share learning relating to smoking in pregnancy with team | Ensure process within smoking cessation services are in place to support women who smoke in pregnancy to stop smoking | Test changes and undertake lessons learned | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Training completed for staff member to support women who smoke in pregnancy, to stop smoking | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Trained staff shared learning relating to smoking in pregnancy with team at smoking cessation team meeting | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.1 | 2023/24WF-0042 | We are working with Community Learning and Development partners to ensure a tiered Suicide Prevention training relating to the Knowledge and Skills Framework for mental health improvement, self harm and suicide prevention across levels; informed, skiled and enhanced is delivered. | Begin delivery of 'Save a Life' informed level training in Orkney | Continued delivery of 'Save a life' training, with promotion of skilled level online learning. Plan for enhanced level training delivery for rest of annual year developed. | Continued delivery of 'Save a Life' training and delivery of 'Scottish Mental Health First Aid' | Continued delivery of 'Save a Life' training and 'Scottish Mental Health First Aid' | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Save a Life training offer commenced | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Save a Life training continuing to be offered and SMFA training organised for next quarter | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.5 | 2023/24SU-0043 | An anchor institution self-assessment is to be undertaken and utalised to develop an NHS Orkney Anchors Strategic Plan by October 2023. | Actively particiapte in the CPP work to implement Community Wealth building initatives. | NHS Orkney to complete self-assessment as an anchor institution | NHS Orkney to formulate an action plan based on the assessment findings | NHS Orkney to implement action plan relating to improving it's position as an anchor institution. | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on other NHS departments may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Met with national anchor leads to share learning. Work ongoing with CPP relating to anchors. Sustainability group considering whether e governance structure in NHS Orkney will be through this group. | Workforce - absence; other - engagment across organisation | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on other NHS departments may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Self-assessment completed and plan developed. Due to go to board in October | Workforce - absence; other - engagment across organisation | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on other NHS departments may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.5 | 2023/24WF-0045 | Through Healthy Working Lives we will promote awareness and deliver training to support the implementation of fair work pracitices and healthy work places in Orkney | Survey completed and interviews arranged with some stakeholders | Communications relating to support services for businesses developed. Interviews with businesses completed | Completion of Health at work needs assessment in Orkney | Implementation of healthy working lives training offer in Orkney | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Survey completed and interviews arranged | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Interviews completed and communications shared on social media relating to relevant training opportunities. | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.5 | 2023/24SU-0046 | Anchor activity is being progressed across partners through the community planning partnership by the Sustainabile Delivery Recovery Group with a focus on Community Wealth Building. | A Community Wealth building workshop has been held with The Orkney Partnership, so that members can better understand the CWB approach and begin to explore how CWB could be implemented in Orkney to inform the delivery of the 2023/30 Orkney Community Plan. | Community planning partners and other organisations will be invited to take place in a series of workshops on the five CWB pillars and the findings of these workshops be used to write a draft plan to implement CWB in Orkney | Orkney CWB plan finalised | Test changes and undertake lessons learned | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Attended workshop | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Continued engagment with CPP and sustainability group. Development of procedure for Community Benefits Portal use in NHS Orkney completed and ready for implementation in Q3/4. | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
6. Health Inequalities | 6.6 | 2023/24SU-0047 | The NHS is a member of the Orkney Islands Council Sustainable Travel Group, through this it is ensured that the needs of patients are considered in an sustainable ttravel planning proposals. Issues faced by patients can also be raised at this forum for consideration. | None Planned | Provide specialist public health input to the Sustainable Travel group including delivering understanding of health opportunities in planning | Provide specialist public health input to the Sustainable Travel group including delivering understanding of health opportunities in planning | Provide specialist public health input to the Sustainable Travel group including delivering understanding of health opportunities in planning | Other | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Contributing through participation in the group | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development | Green | Contributing through participation in the group | Workforce - absence; other - partner engagment | Potential for pressures on small team, particularly if there is absence or posts vacant, to impact on work delivery; pressures on partner organisations may impact on the delivery of work. | Recruited to staffing plan and giving team opportunities for development
1. Primary and Community Care | 1.1 | 2023/24QS-0048 | Progress Primary Care Improvement Plan | None Planned | Meet with GP Sub-Committee to scope CTAC service which can be delivered within current financial envelope | Secure accommodation and work IT around opportunities | Aim to embed most critical actions/elements of the scope. Consider and agree next steps and futher areas for improvement | Other | Lack of suitable accommodation | Reporting through Senior Leadership Team and Area Clinical Forum Status quo to remain | Green | None planned | N/A | N/A | N/A | Amber | Met with GP sub committee and agreement was reached regarding scope of service that can be delivered within our current financial envelope. In meantime practices have received transitional payments for 2023-24 | Other | Suitable premises need to free up to allow the service to commence hopefully by beginning of April 2024. | Status Quo would have to be considered
7. Innovation Adoption | 7.1 | 2023/24QS-0049 | Work with ANIA partners to be progressed to adopt and scall all approved innonvations | None Planned | Meet with Centre for Sustainable Delivery to understand the programmes of work being undertaken to allow a plan to be produced for progressing through local groups and committees | Agree priority areas and set milestones and prioritsation for all to ensure measured outcomes for each opoprtunity | Progress with agreed actions and report through Senior Leadership Team and relevant Governance Committees | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent developmental workstreams. | 1. Clear project plan with clear deliverables. 2. Seek external support as required. | Green | None planned | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent developmental workstreams. | 1. Clear project plan with clear deliverables. 2. Seek external support as required. | Green | Initial meeting with Centre for Sustainability and details shared to allow locally planning to be progressed | Other | The most significant risk to delivering these objectives is the capacity to undertake the necessary reviews, and capacity to then deliver any subsequent developmental workstreams. | 1. Clear project plan with clear deliverables. 2. Seek external support as required.
Note on I2: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on N2: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on S2: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on X2: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other
Note on AC2: u452026: Finance - Non-recurrent funding Finance - Funding not yet agreed Workforce - Recruitment Workforce - Retention Workforce - Absence Workforce - Training, Development and Skills Workforce - Wellbeing Estates Procurement Other