## Improving Health & Wellbeing
Ref | Clinical strategy section | Objective | Success measurement | Lead | Actions 23-24 | Actions 24-25 | Actions 25-26 | Actions 26-27
| Inequalities | Lead NHS Orkney’s work to mitigate the impact of the Cost of Living Crisis in Orkney for staff and the population of Orkney | Satisfactory implementation of the Cost of Living Crisis plan for NHS Orkney. | PHM | Cost of Living Plan received by APF and ACF and implementation commenced | Continued Implementation of plan and it's contribution to the wider Cost of Living work being delivered by the CPP | Assessment and refocus of CPP work if required
|  |  | Implementation of financial inclusion pathways within NHS. |  |  | Embedding of financial inclusion pathways across most relevant NHS services | Review and update of financial inclusion pathways
| Inequalities | Contribute to the delivery of the Child Poverty Strategy and Implementation Plan | Plan is implemented in accordance with specified time scale. | PHM | Contributing through participation in the Cost of Living CPP delivery group | Implementation of plan | Assessment and refocus of CPP action if required
|  |  | Training delivered to staff across health and social care relating to financial inclusion. |  |  | Training delivery to new staff | Training accessible to most relevant staff groups in OHAC
| Inequalities | To work towards maintaining key performance indicator standards in screening programmes | KPIs are maintained or improved | CPH | Monitoring is undertaken by the NHS Orkney Board Screening Coordinator through attendance at National Board Screening Coordinator Groups and local and regional governance groups for the programmes. Actions to address issues are agreed through the meetings. | Review KPIs and address inequalities | Review KPIs and address inequalities | Review KPIs and address inequalities
| Inequality | Work with islands communities to co-design and develop models of care and services that are tailored, effective and sustainable. | Each island has a model of care which works within their island community. | Chief Officer. | First three islands (Papa Westray, Eday and North Ronaldsay) will have plans developed and actioned by March 2024. | Roll out engagement with the next set off island communities. | Roll out engagement with the next set off island communities. | Roll out engagement with the next set off island communities.
| Inequalities | Following the NHS Orkney review of screening inequalities to develop an action plan for addressing screening and inequalities in preparation for further funding being received. | Action plan developed with reduction in inequalities when implemented | CPH | Development of action plan | Implementation of action plan where possible, dependant on funding |  | Assessment of impact on inequalities
| Inequalities | Development of action plan relating to reducing inequalities in screening for people with learning disabilities and people who have experienced intimate partner violence. | Action plan developed with reduction in inequalities when implemented | PHM | Collate the evidence gained from focus and interviews and report findings | Lessons learned from project and action plan implemented
| Inequality | Secure the sustainability of the Islands’ Wellbeing Project and Island Co-ordinators. | IJB funding to be sought and secured for Wellbeing Co-ordinators to continue beyond October 2023. | Chief Officer. | Funding be approved by the IJB
| Inequality | Develop targeted, creative and appropriate community bases responses to support oral health improvement, based on Community Challenge fund model, supporting positive oral health behaviour and access to dental services when needed. | Report on growth of activities to support oral health improvement in community, e.g. visits to toddler, community groups in Orkney. | Head of Primary Care Services / Director of Dentistry / Oral Health Lead
| Smoking | Lead the implementation of smoking tobacco work across multi-agency partners to reduce the impact of tobacco | Development of multi-agency ‘Smoke Free Orkney’ plan | PHM | Plan for cessation in development. Begin planning for Prevention and Protection elements of plan | Implementation of cessation and protection plans and development of prevention aspect of smoke free plan Review service in relation to expected SG Services guidance and complete service development as required. | Implementation of prevention aspect of smoke free plan
| Smoking | Develop Smoking cessation specialist staff to support women through pregnancy. | Service implemented | PHM | Training completed | Assess need for training in other specific high -risk groups
| Smoking | Communications to public are in line with health behaviour change principles | Communications plan developed and implemented | PHM | Communications planning for smoking comms completed. Full plan for completion later in year. | Continued implementation fo the smoking comms plan. Development of departmental comms plan | Delivery of comms plan relating to all aspects of public health work as relevant | Delivery of comms plan relating to all aspects of public health work as relevant
| Alcohol | Refresh ADP Strategy 2026 - 2031 | Ensure a refreshed ADP Strategy is in place | Head of Health and Community Care / ADP Coordinator | N/A | N/A | Engage with services and stakeholders to develop a new Strategy | Approve new Strategy and develop an associated Action Plan
| Alcohol | Prevention and Early Intervention | Fewer people develop problem drug or alcohol use |  | Ensure that those with lived and living experience of alcohol and drug issues who wish to have their voices heard can do so in a meaningful way. | Early identification of those individuals at high risk of alcohol and drug dependence and employ a holistic approach (not focussing solely on substance misuse but the whole needs of the person) recognising other aspects (social, emotional, physical) not just exclusively on their substance use. | Employ and invest in a trauma-informed workforce across the whole of Orkney ADP, who have the skills to recognise and tackle stigma experienced by people affected by substance misuse. | Building resilience into the local community to challenge detrimental embedded culture of problematic alcohol consumption. | Invest through both monetary and time in education and ensure that our children and young people have access to evidence based, appropriate and informative education and harm reduction inclusive all of settings acknowledging that some of our young people may not be in education, training, or employment.
| Alcohol | Developing Recovery Orientated Systems of Care | People access and benefit from effective, integrated, person centred support to achieve their recovery |  | Commission services that are appropriate for the needs of the local population and remove barriers to treatment by piloting other treatment models including assertive outreach. | Services commissioned by the ADP are needs led for those who are accessing them. | Adopt a Recovery Orientated System of Care (ROSC) throughout both the statutory and third sectors providing alcohol and drug treatment services. | Individuals returning to Orkney from residential rehabilitation and / or custody settings are provided with appropriate and seamless transition of through-care and after-care where possible. | Services in the remote and outlying islands of Orkney are delivered with equity of access where possible. | Alcohol and drug treatment services provide access to treatment within 21 days of and individual’s referral to the service. | Clear and easily accessible routes for those who require opiate prescribing therapies and provision of the opiate reversal drug, Naloxone.
| Healthy Weight | Enable clinicians to have health behaviour change orientated conversations including with parents around child healthy weight | Delivery of MAP and healthy beginnings MAP behaviour change training with relevant staff groups. | PHM | Additional member of staff trained to deliver MAP | MAP training delivered | MAP training delivered | MAP training delivered
| Healthy Weight | Lead on the delivery the diabetes and health weight Framework and standards in line with national milestones | Achievement of national milestones | PHM | Implementation plan for 23/24 accepted by SG and work started to implement this. Control it (diabetes ed) has began delivery | Diabetes Framework and Healthy weight standards implemented in line with national guidance |  | Diabetes framework and health weight standards embedded in NHS Orkney
| Physical activity | To increase engagement with physical activity | Pilot completed and evaluated | PH | Assessment of physical activity pilot | Option agreed for ongoing implementation of physcial activity in the weight management programme as per standards | Embedding of physical activity in weight management services as per standdards
| Physical activity | To increase engagement with physical activity | Orkney Strategy developed | PH | Contribute to the development of the physical activity strategy | Support implementation of strategy | Support implementation of strategy
| Physical activity | To increase engagement with physical activity | Island Games delivered | PH/IJB | Island Games population health input | Island Games population health input | Island Games occur
| Public Health | A Public Health Approach to Justice | Vulnerable people are diverted from the justice system wherever possible and those within justice settings are fully supported | PH/DoNMAHP | Ensure that liaison between Scottish Prison Service and local Criminal Justice Service occurs to provide the best possible care for those during arrest, police custody, sentencing and prison. | Support the development of community justice pathways which utilises local and national support networks that allows the inclusion of family members of loved ones in community based support. | Local alternatives to prosecution including therapeutic services, diversionary activities, educational support and employment opportunities are developed and how best to facilitated to access to services, as well as rehabilitation once people are released from custody who require alcohol and drug treatment and support.

## Children & Young People
REF | Clinical Strategy Section | Objective | Success measurement | Lead | Actions 23-24 | Actions 24-25 | Actions 25-26 | Actions 26-27
| Child Health | Contribute to national work on developing a new Child Health System, process mapping and SOPs. | Implementation of system by March 2025 | PHAM | Contributing to national work through attendance at the Scottish Child Health Management Group | Testing and implementation of new system and processes | Routine running of new system using data to inform service development
| Child Health | Monitor childhood immunisation uptake and take appropriate actions to increase vaccination rates and to reduce inequalities | Achieve uptake targets following transformation of service to a Board delivered service. | CPHM | Ongoing monitoring of uptake, actions will be agreed at the Vaccination Management Group | Address any low uptake and introduce any new vaccinations | Address any low uptake and introduce any new vaccinations | Address any low uptake and introduce any new vaccinations
| Child Health | Child and Adolescent Mental Health Service | Waiting times for Child and Adolescent Mental Health Service reduced. | Service Manager - Mental Health Services / Team Leader - CAMHS
| Child Health | Develop the Children's Services Plan 2023-26 | Children's Services Plan is approved and published. | Chief Officer / Corporate Director for Education, Leisure and Housing / Head of Children, Families and Justice Services / Head of Education | Approve the Plan and publish Plan on websites
| Child Health | Refresh the Children's Health Services Plan. | Children's Health Services Plan is developed and approved. | Head of Children, Families and Justice Services / Service Manager (Children's Health Services) | Engage with services to develop a refreshed Service Plan following Service Manager commencing in post. | Approve the Plan
| Child Health | Create additional frontline resource in Speech and Language Therapy. | Waiting times for assessment and treatment reduced. | Head of Children, Families and Justice Services /Lead AHP / Service Manager (Children's Health Services) | Funding be approved by the IJB for additionality | New SaLT in post
| Child Health | Neuro-development assessment pathway | Embed a new Neuro-developmental assessment pathway. | Head of Children, Families and Justice Services / Service Manager (Children's Health Services) | SLA discussion in progress, to review delivery of community and acute based services
| Child Health | Getting it Right for Children, Young People and Families | Children and families affected by alcohol and drug use will be safe, healthy, included and supported |  | Ensure that families affected by a loved one’s alcohol or drug use have access to support in their own right and can be involved in their loved one’s treatment and support where appropriate. | Identify and provide person-centred services specifically for young people who are affected by parental or familial substance misuse. | Ensure that a multi-agency response to supporting children and families is undertaken and information is shared appropriately and in a timely manner to support those most at risk. | Develop and maintain a competent workforce that is able to recognise the impact of Adverse Childhood Experiences (ACEs) and are trauma-informed. | Provide training to develop and maintain a workforce that routinely undertake screening for domestic violence, sexual abuse and sexual exploitation so that services are not drawn to collude with perpetrators in further coercion of the most vulnerable and those experiencing sexual violence and domestic abuse should have their safety and wellbeing needs met through early identification.

## Mental Health
REF | Clinical strategy section | Objective | Success measurement | Lead | Actions 23-24 | Actions 24-25 | Actions 25-26 | Actions 26-27
| Mental Health | Develop a Suicide Prevention Plan | Suicide Prevention Plan Published | Suicide Prevention Task Force Chairs - Chief Officer / Corporate Director for Education, Leisure and Housing | Develop a Suicide Prevention Plan
| Mental Health | Establish a Psychiatric Liasion Service. | Psychiatric Liasion Service Established | Head of Health and Community Care / Service Manager - Mental Health Services | Psychiatrtric Liasion Service model developed and IJB approval sought
| Mental Health |  | Number of days lost from Community Mental Health Services as a result of staffing the mental health transfer bed are reduced. | Service Manager - Mental Health Services
| Mental Health |  | Number of individuals using the mental health transfer bed is reduced | Service Manager - Mental Health Services
| Mental Health | Develop a Mental Health Strategy 2025 - 2030 | Ensure a refreshed Mental Health Strategy is in place | Head of Health and Community Care / Service Manager - Mental Health Services |  | Engage with services and stakeholders to develop a new Strategy | Approve new Strategy and develop an associated Action Plan
| Mental Health | Improved quality of life for individuals experiencing mental health problems, through a person-centred approach, prevention and recovery orientated mental health service provision. |  |  | Further develop a holistic and rights-based approach to recovery focussed practice. | Improve care, treatment and support pathways, including access to in-patient treatment, with the aim of reducing the risk of crisis and the need for off-island treatment. | Development of CLS to build resilience which links people, services and groups as well as developing effective signposting, promoting reduced reliance on statutory services. | Through partnership working to respond to local needs with early years, education, housing, external service providers and local communities. | Improve participation and co-production opportunities by involving individuals and their carers, who have lived experience, thereby utilising their skills and knowledge in service development. | Provide access to new care/treatment pathways e.g. DBI. NHS 24 MH Hub (24/7) cCBT etc. | Work more closely with Public Health for those with mental health conditions to take up health screening and cessation programmes.
| Mental Health | Support for a professional workforce, including effective and appropriate training and strong multi-disciplinary culture. |  |  | Develop CMHN support to provide enhanced capacity for primary care access for people with mild to moderate mental health problems, working in partnership with GP practices. | Focus on the whole person, ensuring that physical and mental health needs are considered equally. | Review the proposed specialist Mental Health training, to support and enhance current clinical services. | Develop training plan to further develop skills of staff within the CMHS and within partner agencies. | Further explore and develop the use of local in-patient and community-based supports in order to prevent a requirement for off island treatment. | Further develop training and support to MHOs. | Build on current Psychology services across all ages, ensuring clear pathway for referrals and interventions. | Develop improved post-diagnostic supports for those with dementia and their carers. | Provide support and training for service providers and carers, for people with dementia, including end of life supports. | Explore and develop models of integrated working, including co-location. | Promote proactive risk enablement approach to treatment and intervention.
| Mental Health | Provision of a range of community-based support services, which promote prevention, self-management, self-reliance and resilience from birth to end of life. |  |  | Develop effective approaches to supporting prevention and self-management of mental health needs, enabling individuals to become self-reliant and resilient. | Develop a range of opportunities for all age groups to connect with their local communities. | Improve upon physical health outcomes through further developing relationships with leisure and third sector providers. | Work in partnership with early years and education to promote mental health and wellbeing. | Develop parenting programmes to support positive child development and personal resilience. | Build on current transitions and discharge pathways including anticipatory care plans, supporting young people from early childhood to become healthy adults. | Develop care pathways for Looked After and Accommodate Children and in secure care.
| Mental Health | Decrease mental health inequality, stigma and discrimination through greater community awareness. |  |  | Improve awareness of mental wellbeing and mental health conditions across all communities, including early years, education, the workplace/employers, social and community settings and at home. | Support individuals to access social and group settings, including clubs and groups through the development of communities. | Continue to develop people friendly communities, raising awareness and enabling improved access to social activities. | Further develop employment and employability opportunities, providing support to employees and employers to achieve a flexible, productive employment environment.
| Mental Health | Improved access to information and communication. |  |  | Ensure that mental health and wellbeing information, advice and guidance is readily available to all individuals and within all communities. NHS Inform | Work with local media, local communities and service providers to provide targeted mental health promotion campaigns. | Improved integration of services between health and social care teams and the third sector. | Promote use of generic, accessible support networks e.g. apps, online programmes (i.e. SilverCloud and CBT), social networks. | Further develop use of TEC. | Improve upon communications systems across statutory services. | Ensure appropriate data sharing is maximised for the benefit of individuals.
| Mental Health | Develop opportunities to enable more effective use of resources accessible through all stakeholder groups and across all communities, to enhance support services to individuals and carers. |  |  | Map current services and available resources, in conjunction with all partners, enabling identification of new opportunities and more effective use of available resources. | Develop partnerships across the statutory, third sectors and local communities, enabling creative ways of providing a range of local supports. | Explore options and opportunities offered to develop local community supports through CLS.
| Mental Health | Improved access to a range of supports for carers. |  |  | Include representation from mental health providers to the Carers Strategy Group to ensure the needs of carers who’s caring responsibilities are in relation to a personal with mental health needs are represented. | Ensure that carers of people living with mental health conditions have their needs considered and views respected. | Develop a range of short break and respite opportunities, working in partnership with local communities and businesses.
| Mental Health | Improvement plan to ensure robust and timely data reporting for CAMHS including CAMHS PT |  |  | Work will be undertaken by the CAMHS team and Health Intelligence to patch and remedy anomalies in the CAMHS aggregate data | Maintain and embed the work completed in quarter 1 to ensure robust and accurate data reporting in relation to CAMHS aggregate data. Undertake GAP analysis of CAMHS CAPTND data | Maintain and embed the work completed in quarter 1 to ensure robust and accurate data reporting in relation to CAMHS aggregate data. Scope out how to deliver against the gap analysis findings.
| Mental Health | As part of the recommendations from the Mental Wealth Commission, action has been taken forward within Psychological Therapy relating to adequate support and equal access to support minority groups. Collaboration with Regional services to ensure equitable as close to home.
| Mental Health | To work with partner agencies to develop a suicide prevention and early intervention approach which is embedded across services | Embedded suicide prevention approach |  | Development of a tiered training approach for delivery in Orkney relating to the Knowledge and Skills Framework for mental health improvement, self harm and suicide prevention across levels; informed, skilled and enhanced. | Delivery of tiered sucide prevention training model in Orkney. | Work with partner agencies including the CPP to deliver on plans to reduce the wider impacts of health which can influence deaths by suicide.
| Medication Assisted Treatment | All people accessing services have the option to start MAT from the same day of presentation. | This means that instead of waiting for days, weeks or months to get on a medication like methadone or buprenorphine, a person with opioid dependence can have the choice to begin medication on the day they ask for help |  | We will complete the full ORT prescribing guidelines to meet the statement above. | We will complete the full ORT prescribing guidelines to meet the statement above. | With support from MIST and local IT support our system is going to be upgraded so that we can provide comprehensive patient data.
| Medication Assisted Treatment | All people are supported to make an informed choice on what medication to use for MAT and the appropriate dose. | People will decide which medication they would like to be prescribed and the most suitable dose options after a discussion with their worker about the effects and sideeffects. People will be able to change their decision as circumstances change. There should also be a discussion about dispensing arrangements and this should be reviewed regularly. |  | We will complete the full ORT prescribing guidelines. | We will set up process to complete experiential data. | We will set up process to complete experiential data.
| Medication Assisted Treatment | All people at high risk of drug-related harm are proactively identified and offered support to commence or continue MAT. | If a person is thought to be at high risk because of their drug use, then workers from substance use services will contact the person and offer support including MAT. |  | We will review our internal pathway between ED and ODAT | Within the non-fatal overdose pathway, SAS alert the ODAT patients admitted to Hospital with overdose. These referrals will be actioned within 72 hours. | We will set up similar pathways with police department and third sector organisations. | We will set up similar pathways with police department and third l people are offered evidencebased harm reduction at the point of MAT delivery sector organisations.
| Medication Assisted Treatment | People are offered evidencebased harm reduction at the point of MAT delivery. | While a person is in treatment and prescribed medication, they are still able to access harm reduction services – for example, needles and syringes, BBV testing, injecting risk assessments, wound care and naloxone. They would be able to receive these from a range of providers including their treatment service, and this would not affect their treatment or prescription. |  | We will record offer of naloxone training and take-home naloxone will be added to our prescribing guidelines when complete. | We will review existing Information Sharing Protocols.
| Medication Assisted Treatment | All people will receive support to remain in treatment for as long as requested. | A person is given support to stay in treatment for as long as they like and at key transition times such as leaving hospital or prison. People are not put out of treatment. There should be no unplanned discharges. When people do wish to leave treatment they can discuss this with the service, and the service will provide support to ensure people leave treatment safely. Treatment services value the treatment they provide to all the people who are in their care. People will be supported to stay in treatment especially at times when things are difficult for them |  | We will set up process to complete experiential data. | We will set up process with MIST support to provide comprehensive patient data.
| Medication Assisted Treatment | The system that provides MAT is psychologically informed (tier 1); routinely delivers evidence-based low intensity psychosocial interventions (tier 2); and supports individuals to grow social networks. | This means that instead of waiting for days, weeks or months to get on a medication like methadone or buprenorphine, a person with opioid dependence can have the choice to begin medication on the day they ask for help |  | We have been selected as a pilot for Trauma based care which will help progress access to addictions clinical psychology. | There is limited recovery groupwork locally for follow on care and we will scope how we might improve this
| Medication Assisted Treatment | All people have the option of MAT shared with Primary Care. | People who choose to will be able to receive medication or support through primary care providers. These may include GPs and community pharmacy. Care provided would depend on the GP or community pharmacist as well as the specialist treatment service |  | he GPWSI will continue to work with Primary Care colleagues to develop further interaction. However, currently Primary Care are unable to offer a shared MAT service.
| Medication Assisted Treatment | All people receive trauma informed care | The treatment service people use recognises that many people who use their service may have experienced trauma, and that this may continue to impact on them in various ways. The services available and the people who work there, will respond in a way that supports people to access, and remain in, services for as long as they need to, in order to get the most from treatment. They will also offer people the kind of relationship that promotes recovery, does not cause further trauma or harm, and builds resilience. |  | We have been selected as a pilot for Trauma based care which will help progress access to addictions clinical psychology.

## Long Term Conditions
REF | Clinical strategy section | Objective | Success measurement | Lead | Actions 23-24 | Actions 24-25 | Actions 25-26 | Actions 26-27
| Long terms conditions | Plan, implement and monitor the Winter vaccination programmes. | Provision of Winter vaccinations in line with national policy and targets. | CPHM | Ongoing review of plans in line with national updates, actions will be agreed at the Vaccination Management Group | Lessons learned from delivery and implementation of any further winter vaccination programmes | Lessons learned from delivery and implementation of any further winter vaccination programmes
| Long term conditions - cancer | Improve early detection of cancer | Screening uptake targets reached | CPH | screening promotion | screening promotion and analysis of uptake and implementation of improvement plans | screening promotion and analysis of uptake and implementation of improvement plans | screening promotion and analysis of uptake and implementation of improvement plans
| Long Term Conditions | Engage in the Getting It Right For Everyone (GIRFE) national pathfinder programme, with a focus in Orkney on Frailty and Ageing Well Project. | Number of hospital avoidance due to early intervention and support for people with frailty. | Lead AHP
| Long Term Conditions | Support more older people to live safely at home for longer. | Reduction in rate of falls in older people population. | Lead AHP | Ongoing workstream with physio lead and close links to GIRFE has seen falls reduction
| Long Term Conditions |  | The percentage of telecare users who have switched to digital from analogue is increased. | Head of Health and Community Care / Service Manager (Community Care)
| Long Term Conditions |  | Unmet need hours of Care at Home provision are reduced. | Head of Health and Community Care / Service Manager (Community Care)
| Long Term Conditions |  | Number of service users receiving care at home support is increased. | Head of Health and Community Care / Service Manager (Community Care)
| Long Term Conditions | Set out a plan and approach to be taken forward to support early detection and management of key cardiovascular risk factor conditions: diabetes, high blood pressure and high cholesterol |  |  | Plan for smoking cessation in development following options appraisal. Begin to plan for additional elements which are protection and preventation. Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded | Discussion with GP Cluster to agree way forward Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded | Following initial discussion with GP cluster ensure a clear and measured action plan is created to address Develop multiagency plan for smoking cessation Implementing type 2 Diabetes framework through multiagency steering group, which includes ensuring core data set is recorded Report completion of physical activity pilot which will support recomendations in relation to incorpate physical activity in weight management
| Long Term Conditions | Progress Primary Care Improvement Plan |  |  | Meet with GP Sub-Committee to scope CTAC service which can be delivered within current financial envelope. Meeting has taken place, current financial envelope will not allow for delivery of equitable CTAC for all of population | Secure accommodation and work IT around opportunities